{"text_format":"2","workbook":"xls","n_sheets":4,"sheets":["Master Deliverables Table","Initial deliverable table","Deliverables- from sections","Milestones- fromsections"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Master Deliverables Table","index":0,"n_rows":123,"n_cols":11,"rows_kept":123,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
[null,"Combined Deliverables Table"]
[null,"- From initial table and the text of each activity the DoW"]
[]
[null,"Deliverable #","Activity","Activity Specific Deliverable Number","Deliverable description","Planned Delivery Month","Actual Delivery Month","Current Status\n ( x of 4 )","Nature ","Dissemination Level ","Lead Consortium Member"]
[null,"D1","NA4","NA4.01","Creation of Public EXPReS web-site ",2,"xxx","xxx","O","PU","xxx"]
[null,"D2","JRA1","J1.1","Data acquisition requirements document",2,"xxx","xxx","R","PU","xxx"]
[null,"D3","JRA1","J1.2","Protocols strategic document",2,"xxx","xxx","R","PU","xxx"]
[null,"D4","NA2","NA2.01","EVN-NREN meeting No. 1 (under auspices of EXPReS)",3,"xxx","xxx","R","PP","xxx"]
[null,"D5","SA1","SA1.1","Central data link control",3,"xxx","xxx","D","PU","xxx"]
[null,"D6","NA3","NA3.1","First meeting of eVSAG under auspices of EXPReS",4,"xxx","xxx","R","PP","xxx"]
[null,"D7","NA4","NA4.02","Creation of EXPReS web-based management tools",4,"xxx","xxx","O","PP","xxx"]
[null,"D8","JRA1","J1.3","Visualization software",4,"xxx","xxx","P","PU","xxx"]
[null,"D9","JRA1","J1.4","Correlator design specification",5,"xxx","xxx","R","PU","xxx"]
[null,"D10","NA4","NA4.03","Generation of PR material (phase 1) ",6,"xxx","xxx","O","PU","xxx"]
[null,"D11","SA1","SA1.2","Job preparation utilities",6,"xxx","xxx","D","PU","xxx"]
[null,"D12","SA1","SA1.3","Fast/adaptive scheduling tools",6,"xxx","xxx","D","PU","xxx"]
[null,"D13","SA2","SA2.01","Feasibility study of the last-mile connection to the nearest NREN node for participant CNIG-IGN",6,"xxx","xxx","R","PU","CNIG-IGN"]
[null,"D14","SA2","SA2.02","Feasibility study of the last-mile connection to the nearest NREN node for participant MPIfR",6,"xxx","xxx","R","PU","MPIfR"]
[null,"D15","SA2","SA2.03","Equipment of the last-mile infrastructure for participant INAF (telescope in Medicina)",6,"xxx","xxx","O","PU","INAF"]
[null,"D16","SA2","SA2.04","Feasibility study of the last-mile connections to the nearest GEANT NREN node for participant CAS (Shanghai, Urumqi, Miyun, Yunnan )",6,"xxx","xxx","R","PU","CAS"]
[null,"D17","SA2","SA2.05","Feasibility study of the last-mile connection to the nearest NREN node for participant VIRAC",6,"xxx","xxx","R","PU","VIRAC"]
[null,"D18","SA2","SA2.06","Feasibility study of the last-mile connection to the nearest NREN node for participant HRAO",6,"xxx","xxx","R","PU","HRAO"]
[null,"D19","SA2","SA2.07","Feasibility study of the last-mile connection to the nearest NREN node for participant NAIC (Arecibo)",6,"xxx","xxx","R","PU","NAIC"]
[null,"D20","SA2","SA2.08 ","Feasibility study of the last-mile connection to the nearest NREN node for participant TIGO",6,"xxx","xxx","R","PU","TIGO"]
[null,"D21","SA2","SA2.09","Feasibility study of the last-mile connection to AARNET for participant CSIRO",6,"xxx","xxx","R","PU","AARNET"]
[null,"D22","JRA1","J1.5","Overall design document",6,"xxx","xxx","R","PU","xxx"]
[null,"D23","JRA1","J1.6","eVLBI-Grid design document",6,"xxx","xxx","R","PU","xxx"]
[null,"D24","JRA1","J1.7","eVLBI fringes PC-EVN",7,"xxx","xxx","D","PU","xxx"]
[null,"D25","JRA1","J1.8","LOFAR connection strategic document",7,"xxx","xxx","R","PU","xxx"]
[null,"D26","JRA1","J1.9","Data acquisition design document",8,"xxx","xxx","R","PU","xxx"]
[null,"D27","SA1","SA1.4","eMERLIN VSI interfaces design",9,"xxx","xxx","P","PU","xxx"]
[null,"D28","SA1","SA1.5","Selective data processor controls",9,"xxx","xxx","D","PU","xxx"]
[null,"D29","SA2","SA2.10","e-VLBI test observations, Medicina",10,"xxx","xxx","R","PU","INAF"]
[null,"D30","JRA1","J1.10","eVLBI-Grid interface document",10,"xxx","xxx","R","PU","xxx"]
[null,"D31","NA2","n/a","NA2 annual report No. 2 (as part of EXPReS Ann. Rep No. 2)",24,"xxx","xxx",null,null,"xxx"]
[null,"D32","NA1","NA1.01","Annual report (incl. Financial information) to EC ",12,"xxx","xxx","R","PP","xxx"]
[null,"D33","NA2","NA2.02","NA2 annual report No. 1 (as part of EXPReS Ann. Rep No. 1)",12,"xxx","xxx","R","PP","xxx"]
[null,"D34","NA4","NA4.04","e-VLBI Demonstration and attendance at Network events.",12,"xxx","xxx","O","PU","xxx"]
[null,"D35","SA1","SA1.5","Network Protocol decision",12,"xxx","xxx","D","PU","xxx"]
[null,"D36","SA1","SA1.7","Monitored information handling modules",12,"xxx","xxx","D","PU","xxx"]
[null,"D37","SA2","SA2.011","Equipment of the last-mile infrastructure for participant MRO",12,"xxx","xxx","O","PU","MRO"]
[null,"D38","SA2","SA2.12","Construction and equipment of the last-mile infrastructure for participant CNIG-IGN",12,"xxx","xxx","O","PU","CNIG-IGN"]
[null,"D39","SA2","SA2.13 ","Construction and equipment of the last-mile infrastructure for participant MPIfR",12,"xxx","xxx","O","PU","MPIfR"]
[null,"D40","SA1","SA1.8","Monitoring processes",12,"xxx","xxx","D","PU","xxx"]
[null,"D41","JRA1","J1.11","Protocols performance report",13,"xxx","xxx","R","PU","xxx"]
[null,"D42","JRA1","J1.12","Software correlator core",14,"xxx","xxx","P","PU","xxx"]
[null,"D43","JRA1","J1.13","Software data product",15,"xxx","xxx","P","PU","xxx"]
[null,"D44","SA1","SA1.10","Real-time data processor control software",15,"xxx","xxx","P","PU","xxx"]
[null,"D45","SA1","SA1.9","Tests using local Jodrell Bank home e-MERLIN telescope",15,"xxx","xxx","D","PU","xxx"]
[null,"D46","NA3","NA3.2","eVSAG meeting No. 2",16,"xxx","xxx","R","PP","xxx"]
[null,"D47","SA1","SA1.11","Real-time Pipeline",16,"xxx","xxx","D","PU","xxx"]
[null,"D48","NA2","NA2.03","EVN-NREN meeting No. 2 ",18,"xxx","xxx","R","PP","xxx"]
[null,"D49","NA4","NA4.05 ","Generation of new PR material (phase 2)",18,"xxx","xxx","O","PU","xxx"]
[null,"D50","SA1","SA1.12","Visibility monitor",18,"xxx","xxx","D","PU","xxx"]
[null,"D51","SA1","SA1.13","Tested software for operational improvements",18,"xxx","xxx","D","PU","xxx"]
[null,"D52","SA1","SA1.14","Test using remote e-MERLIN telescope",18,"xxx","xxx","D","PU","xxx"]
[null,"D53","SA1","SA1.16 ","VSI support software",18,"xxx","xxx","D","PU","xxx"]
[null,"D54","SA1","SA1.15 ","VSI Interfaces",18,"xxx","xxx","D","PU","xxx"]
[null,"D55","SA2","SA2.14","10 Gbps link upgrade between MERLIN and JIVE",18,"xxx","xxx","O","PU","MERLIN, JIVE"]
[null,"D56","SA2","SA2.15","e-VLBI test observations, Metsahovi",18,"xxx","xxx","R","PU","MRO"]
[null,"D57","SA2","SA2.16","Construction and equipment of the last-mile infrastructure for participant Shanghai",18,"xxx","xxx","O","PU","CAS"]
[null,"D58","SA2","SA2.17 ","Construction and equipment of the last-mile infrastructure in AARNET to allow connection of participant CSIRO",18,"xxx","xxx","O","PU","AARNET,CSIRO"]
[null,"D59","SA2","SA2.18","Construction and equipment of the last-mile infrastructure for participant Urumqi",18,"xxx","xxx","O","PU","CAS"]
[null,"D60","SA2","SA2.19 ","Construction and equipment of the last-mile infrastructure for participant Miyun",18,"xxx","xxx","O","PU","CAS"]
[null,"D61","SA2","SA2.20 ","Construction and equipment of the last-mile infrastructure for participant Kunming",18,"xxx","xxx","O","PU","CAS"]
[null,"D62","SA2","SA2.21 ","Construction and equipment of the last-mile infrastructure for participant VIRAC",18,"xxx","xxx","O","PU","VIRAC"]
[null,"D63","SA2","SA2.22 ","Equipment of the last-mile infrastructure for participant NAIC",18,"xxx","xxx","O","PU","NAIC"]
[null,"D64","SA2","SA2.23 ","Construction and equipment of the last-mile infrastructure for participant TIGO",18,"xxx","xxx","O","PU","TIGO"]
[null,"D65","SA2","SA2.24","AARNET connectivity  enhancements",18,"xxx","xxx","O ","PU","AARNET"]
[null,"D66","JRA1","J1.14","Data acquisition interface document",18,"xxx","xxx","R","PU","xxx"]
[null,"D67","JRA1","J1.15","LOFAR station interface report",18,"xxx","xxx","R","PU","xxx"]
[null,"D68","JRA1","J1.16","Software for workflow management",18,"xxx","xxx","P","PU","xxx"]
[null,"D69","SA2","SA2.25","Feasibility study of the last-mile connection to the nearest GÉANT node for participant INAF (Sardinia)",20,"xxx","xxx","R","PU","INAF"]
[null,"D70","SA2","SA2.26 ","10 Gbps link between UniMan and OSO for ultra-VLBI tests",20,"xxx","xxx","O","PU","UniMan,OSO"]
[null,"D71","SA1","SA1.17 ","Flexible local GE network",21,"xxx","xxx","D","PU","xxx"]
[null,"D72","SA2","SA2.27","e-VLBI test observations, Effelsberg",21,"xxx","xxx","R","PU","MPIfR"]
[null,"D73","SA2","SA2.28","e-VLBI test observations, Metsahovi",22,"xxx","xxx","R","PU","ATNF"]
[null,"D74","SA2","SA2.29","e-VLBI test observations, Yebes",22,"xxx","xxx","R","PU","OAN"]
[null,"D75","JRA1","J1.17","Software for correlation on cluster",23,"xxx","xxx","P","PU","xxx"]
[null,"D76","JRA1","J1.18","Data acquisition test report",23,"xxx","xxx","R","PU","xxx"]
[null,"D77","JRA1","J1.19","Data acquisition prototype at telescope",23,"xxx","xxx","P","PU","xxx"]
[null,"D78","JRA1","J1.20","Overall broadband demonstration",23,"xxx","xxx","D","PU","xxx"]
[null,"D79","JRA1","J1.21","Software cluster correlation",23,"xxx","xxx","P","PU","xxx"]
[null,"D80","JRA1","J1.22","First fringes software correlator",23,"xxx","xxx","D","PU","xxx"]
[null,"D81","NA1","NA1.02","Annual report (incl. Financial information) to EC ",24,"xxx","xxx","R","PP","xxx"]
[null,"D82","NA2","NA2.04","NA2 annual report No. 2 (as part of EXPReS Ann. Rep No. 2)",24,"xxx","xxx","R","PP","xxx"]
[null,"D83","NA4","NA4.06 ","e-VLBI Demonstration and attendance at Network events.",24,"xxx","xxx","O","PU","xxx"]
[null,"D84","SA1","SA1.18","Network monitoring tools",24,"xxx","xxx","D","PU","xxx"]
[null,"D85","SA1","SA1.19","Multiple e-MERLIN  telescope  tests",24,"xxx","xxx","D","PU","xxx"]
[null,"D86","SA2","SA2.30 ","Construction and equipment of the last-mile infrastructure for participant HartRAO",24,"xxx","xxx","O","PU","HRAO"]
[null,"D87","JRA1","J1.23","Software to collect distributed output",24,"xxx","xxx","P","PU","xxx"]
[null,"D88","NA2","NA2.05","EVN-NREN meeting No. 3",26,"xxx","xxx","R","PP","xxx"]
[null,"D89","NA2","NA2.06","EVN-NREN representatives present EXPReS networking results at the e-VLBI Science & Technology Workshop ",26,"xxx","xxx","R","PU","xxx"]
[null,"D90","NA2","n/a","EVN-NREN meeting ","n/a","xxx","xxx",null,null,"xxx"]
[null,"D91","NA3","NA3.3","eVSAG meeting No. 3",26,"xxx","xxx","R","PP","xxx"]
[null,"D92","JRA1","J1.24","Software to create data product from distributed correlation ",27,"xxx","xxx","P","PU","xxx"]
[null,"D93","JRA1","J1.25","Software routing",29,"xxx","xxx","P","PU","xxx"]
[null,"D94","NA3","NA3.4","e-VLBI Workshop held in Onsala",30,"xxx","xxx","O","PU","xxx"]
[null,"D95","SA1","SA1.20 ","Improved network applications",30,"xxx","xxx","D","PU","xxx"]
[null,"D96","SA1","SA1.21","Monitoring user interfaces",30,"xxx","xxx","D","PU","xxx"]
[null,"D97","SA2","SA2.31","e-VLBI test observations, Urunqi",30,"xxx","xxx","R","PU","CAS"]
[null,"D98","SA2","SA2.32","e-VLBI test observations, Mijun",30,"xxx","xxx","R","PU","CAS"]
[null,"D99","SA2","SA2.33","e-VLBI test observations, Kunming",30,"xxx","xxx","R","PU","CAS"]
[null,"D100","SA2","SA2.34","e-VLBI test observations, VIRAC",30,"xxx","xxx","R","PU","VIRAC"]
[null,"D101","SA2","SA2.35","e-VLBI test observations, HRAO",30,"xxx","xxx","R","PU","HRAO"]
[null,"D102","SA2","SA2.36","e-VLBI test observations, NAIC, Arecibo",30,"xxx","xxx","R","PU","NAIC"]
[null,"D103","SA2","SA2.37","e-VLBI test observations, TIGO",30,"xxx","xxx","R","PU","TIGO"]
[null,"D104","SA2","SA2.38 ","Construction and equipment of the last-mile infrastructure for participant INAF (Sardinia)",30,"xxx","xxx","O","PU","INAF"]
[null,"D105","JRA1","J1.26","eMERLIN interface available",30,"xxx","xxx","P","PU","xxx"]
[null,"D106","JRA1","J1.27","Fringes with new routing",31,"xxx","xxx","D","PU","xxx"]
[null,"D107","NA3","NA3.5","Publication of e-VLBI Workshop proceedings",32,"xxx","xxx","R","PU","xxx"]
[null,"D108","JRA1","J1.28 ","Software distributed correlation",33,"xxx","xxx","P","PU","xxx"]
[null,"D109","JRA1","J1.29","First fringes Grid correlator",34,"xxx","xxx","D","PU","xxx"]
[null,"D110","JRA1","J1.30 ","First fringes on FABRIC",35,"xxx","xxx","D","PU","xxx"]
[null,"D111","NA1","NA1.03 ","Annual report (incl. Financial information) to EC ",36,"xxx","xxx","R","PP","xxx"]
[null,"D112","NA1","NA1.04 ","Final Report to Board and EC ",36,"xxx","xxx","R","PP","xxx"]
[null,"D113","NA1","NA1.05 ","Final Plan for using and disseminating knowledge",36,"xxx","xxx","R","PP","xxx"]
[null,"D114","NA1","NA1.06","Implementation of the Gender Action Plan",36,"xxx","xxx","R","PP","xxx"]
[null,"D115","NA1","NA1.07","Raising public participation and awareness ",36,"xxx","xxx","R","PU","xxx"]
[null,"D116","NA2","NA2.07","NA2 annual & Final reports ",36,"xxx","xxx","R","PP","xxx"]
[null,"D117","NA4","NA4.07 ","e-VLBI Demonstration and attendance at network events.",36,"xxx","xxx","O","PU","xxx"]
[null,"D118","JRA1","J1.31","Final report",36,"xxx","xxx","R","PU","xxx"]

{"sheet":"Initial deliverable table","index":1,"n_rows":124,"n_cols":8,"rows_kept":124,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
[null,"Deliverables Table"]
[null,"- from front table of DOW"]
[]
[]
[null,"Deliverable #","Activity #","Deliverable title"," Lead Participant ","Planned Delivery month ","Actual Delivery Month ","Current Status"]
[null,"D1","NA4","Creation of Public EXPReS web-site ","JIVE",2]
[null,"D2","JRA1","Data acquisition requirements document","MRO",2]
[null,"D3","JRA1","Protocols strategic document","JBO",2]
[null,"D4","NA2","EVN-NREN meeting No. 1 (under auspices of EXPReS)","DANTE",3]
[null,"D5","SA1","Central data link control","JIVE",3]
[null,"D6","NA3","First meeting of eVSAG under auspices of EXPReS","OSO",4]
[null,"D7","NA4","Creation of EXPReS web-based management tools","JIVE",4]
[null,"D8","JRA1","Visualization software","JIVE",4]
[null,"D9","JRA1","Correlator design specification","JIVE",5]
[null,"D10","NA4","Generation of PR material (phase 1)",null,6]
[null,"D11","SA1","Job preparation utilities","JIVE",6]
[null,"D12","SA1","Fast/adaptive scheduling tools","JIVE",6]
[null,"D13","SA2","Feasibility study of the last-mile connection to the nearest GÉANT node for participant CNIG-IGN","CNIG-IGN",6]
[null,"D14","SA2","Feasibility study of the last-mile connection to the nearest GÉANT node for participant MPIfR","MPIfR",6]
[null,"D15","SA2","Equipment of the last-mile infrastructure for participant INAF (telescope in Medicina)","INAF",6]
[null,"D16","SA2","Feasibility study of the last-mile connections to the nearest GÉANT node for participant CAS (Shanghai, Urumqi, Miyun, Yunnan )","CAS",6]
[null,"D17","SA2","Feasibility study of the last-mile connection to the nearest GÉANT node for participant VIRAC","VIRAC",6]
[null,"D18","SA2","Feasibility study of the last-mile connection to the nearest GÉANT node for participant HRAO","HRAO",6]
[null,"D19","SA2","Feasibility study of the last-mile connection to the nearest GÉANT node for participant NAIC (Arecibo)","NAIC",6]
[null,"D20","SA2","Feasibility study of the last-mile connection to the nearest GÉANT node for participant TIGO","TIGO",6]
[null,"D21","SA2","Feasibility study of the last-mile connection to AARNET for participant CSIRO","AARNET",6]
[null,"D22","JRA1","Overall design document","ALL",6]
[null,"D23","JRA1","eVLBI-Grid design document","PSNC",6]
[null,"D24","JRA1","eVLBI fringes PC-EVN","OSO",7]
[null,"D25","JRA1","LOFAR connection strategic document","ASTRON",7]
[null,"D26","JRA1","Data acquisition design document","MRO",8]
[null,"D27","SA1","eMERLIN VSI interfaces design","UniMan",9]
[null,"D28","SA1","Selective data processor controls","JIVE",9]
[null,"D29","SA2","e-VLBI test observations, Medicina","INAF",10]
[null,"D30","JRA1","eVLBI-Grid interface document","OSNC",10]
[null,"D31","NA2","NA2 annual report No. 2 (as part of EXPReS Ann. Rep No. 2)","JIVE",24]
[null,"D32","NA1","Annual report (incl. Financial information) to EC","JIVE",12]
[null,"D33","NA2","NA2 annual report No. 1 (as part of EXPReS Ann. Rep No. 1)","JIVE",12]
[null,"D34","NA4","e-VLBI Demonstration and attendance at Network events.","JIVE",12]
[null,"D35","SA1","Network protocol decision","JIVE",12]
[null,"D36","SA1","Monitored information handling modules","JIVE",12]
[null,"D37","SA2","Equipment of the last-mile infrastructure for participant MRO","MRO",12]
[null,"D38","SA2","Construction and equipment of the last-mile infrastructure for participant CNIG-IGN","CNIG-IGN",12]
[null,"D39","SA2","Construction and equipment of the last-mile infrastructure for participant MPIfR","MPIfR",12]
[null,"D40","SA1","Monitoring processes","JIVE",12]
[null,"D41","JRA1","Protocols performance report","JBO",13]
[null,"D42","JRA1","Software correlator core","JIVE",14]
[null,"D43","JRA1","Software data product","JIVE",15]
[null,"D44","SA1","Real-time data processor control software","JIVE",15]
[null,"D45","SA1","Tests using local Jodrell Bank home e-MERLIN telescope","UniMan",15]
[null,"D46","NA3","eVSAG meeting No. 2","OSO",16]
[null,"D47","SA1","Real-time Pipeline","JIVE",16]
[null,"D48","NA2","EVN-NREN meeting No. 2","JIVE",18]
[null,"D49","NA4","Generation of new PR material (phase 2)","DANTE",18]
[null,"D50","SA1","Visibility monitor","JIVE",18]
[null,"D51","SA1","Tested software for operational improvements","JIVE",18]
[null,"D52","SA1","Test using remote e-MERLIN telescope","UniMan",18]
[null,"D53","SA1","VSI support software","JIVE",18]
[null,"D54","SA1","VSI Interfaces","JIVE",12]
[null,"D55","SA2","10 Gbps link upgrade between MERLIN and JIVE","MERLIN, JIVE",18]
[null,"D56","SA2","e-VLBI test observations, Metsahovi","MRO",18]
[null,"D57","SA2","Construction and equipment of the last-mile infrastructure for participant Shanghai","CAS",18]
[null,"D58","SA2","Construction and equipment of the last-mile infrastructure in AARNET to allow connection of participant CSIRO","AARNET, CSIRO",18]
[null,"D59","SA2","Construction and equipment of the last-mile infrastructure for participant Urumqi","CAS",18]
[null,"D60","SA2","Construction and equipment of the last-mile infrastructure for participant Miyun","CAS",18]
[null,"D61","SA2","Construction and equipment of the last-mile infrastructure for participant Kunming","CAS",18]
[null,"D62","SA2","Construction and equipment of the last-mile infrastructure for participant VIRAC","VIRAC",18]
[null,"D63","SA2","Equipment of the last-mile infrastructure for participant NAIC","NAIC",18]
[null,"D64","SA2","Construction and equipment of the last-mile infrastructure for participant TIGO","TIGO",18]
[null,"D65","SA2","AARNET connectivity enhancements","AARNET",18]
[null,"D66","JRA1","Data acquisition interface document","MPI",18]
[null,"D67","JRA1","LOFAR station interface report","ASTRON",18]
[null,"D68","JRA1","Software for workflow management","PSNC",18]
[null,"D69","SA2","Feasibility study of the last-mile connection to the nearest GÉANT node for participant INAF (Sardinia)","INAF",20]
[null,"D70","SA2","10 Gbps link between UniMan and OSO for ultra-VLBI tests","UniMan, OSO",20]
[null,"D71","SA1","Flexible local GE network","JIVE",21]
[null,"D72","SA2","e-VLBI test observations, Effelsberg","MPIfR",21]
[null,"D73","SA2","e-VLBI test observations, Metsahovi","ATNF",22]
[null,"D74","SA2","e-VLBI test observations, Yebes","OAN",22]
[null,"D75","JRA1","Software for correlation on cluster","JIVE",23]
[null,"D76","JRA1","Data acquisition test report","MPI",23]
[null,"D77","JRA1","Data acquisition prototype at telescope","OSO",23]
[null,"D78","JRA1","Overall broadband demonstration","JIVE",23]
[null,"D79","JRA1","Software cluster correlation","JIVE",23]
[null,"D80","JRA1","First fringes software correlator","JIVE",23]
[null,"D81","NA1","Annual report (incl. Financial information) to EC","JIVE",24]
[null,"D82","NA2","NA2 annual report No. 2 (as part of EXPReS Ann. Rep No. 2)","JIVE",24]
[null,"D83","NA4","e-VLBI Demonstration and attendance at Network events.",null,24]
[null,"D84","SA1","Network monitoring tools","JIVE",24]
[null,"D85","SA1","Multiple e-MERLIN telescope tests","UniMan",24]
[null,"D86","SA2","Construction and equipment of the last-mile infrastructure for participant HartRAO","HRAO",24]
[null,"D87","JRA1","Software to collect distributed output","JIVE",24]
[null,"D88","NA2","EVN-NREN meeting No. 3","DANTE",26]
[null,"D89","NA2","EVN-NREN representatives present EXPReS networking results at the e-VLBI Science & Technology Workshop ","DANTE",26]
[null,"D90","NA2","EVN-NREN meeting ","DANTE"]
[null,"D91","NA3","eVSAG meeting No. 3","OSO",26]
[null,"D92","JRA1","Software to create data product from distributed correlation ","JIVE",27]
[null,"D93","JRA1","Software routing","PSNC",29]
[null,"D94","NA3","e-VLBI Workshop held in Onsala",null,30]
[null,"D95","SA1","Improved network applications","JIVE",30]
[null,"D96","SA1","Monitoring user interfaces","JIVE",30]
[null,"D97","SA2","e-VLBI test observations, Urunqi","CAS",30]
[null,"D98","SA2","e-VLBI test observations, Mijun","CAS",30]
[null,"D99","SA2","e-VLBI test observations, Kunming","CAS",30]
[null,"D100","SA2","e-VLBI test observations, VIRAC","VIRAC",30]
[null,"D101","SA2","e-VLBI test observations, HRAO","HRAO",30]
[null,"D102","SA2","e-VLBI test observations, NAIC, Arecibo","NAIC",30]
[null,"D103","SA2","e-VLBI test observations, TIGO","TIGO",30]
[null,"D104","SA2","Construction and equipment of the last-mile infrastructure for participant INAF (Sardinia)","INAF",30]
[null,"D105","JRA1","eMERLIN interface available","JBO",30]
[null,"D106","JRA1","Fringes with new routing","JIVE",31]
[null,"D107","NA3","Publication of e-VLBI Workshop proceedings","OSO",32]
[null,"D108","JRA1","Software distributed correlation","JIVE",33]
[null,"D109","JRA1","First fringes Grid correlator","JIVE",34]
[null,"D110","JRA1","First fringes on FABRIC","JIVE",35]
[null,"D111","NA1","Annual report (incl. Financial information) to EC","JIVE",36]
[null,"D112","NA1","Final Report to Board and EC","JIVE",36]
[null,"D113","NA1","Final Plan for using and disseminating knowledge","JIVE",36]
[null,"D114","NA1","Implementation of the Gender Action Plan","JIVE",36]
[null,"D115","NA1","Raising public participation and awareness","JIVE",36]
[null,"D116","NA2","NA2 annual & Final reports ","JIVE",36]
[null,"D117","NA4","e-VLBI Demonstration and attendance at network events.","JIVE",36]
[null,"D118","JRA1","Final report","JIVE",36]

{"sheet":"Deliverables- from sections","index":2,"n_rows":122,"n_cols":8,"rows_kept":122,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
[null,"Deliverables"]
[null,"- as taken from each activity's section"]
[]
[]
[null,"Activity","Deliverable No ","Deliverable title","Delivery date ","Nature ","Dissemination Level ","Lead Consortium Member"]
[null,"JRA1","DJ1.1","Data acquisition requirements document",2,"R","PU"]
[null,"JRA1","DJ1.2","Protocols strategic document",2,"R","PU"]
[null,"NA4","DNA4.01","Creation of Public EXPReS web-site ",2,"O","PU"]
[null,"NA2","DNA2.01","EVN-NREN meeting No. 1 (under auspices of EXPReS)",3,"R","PP"]
[null,"SA1","DSA1.1","Central data link control",3,"D","PU"]
[null,"JRA1","DJ1.3","Visualization software",4,"P","PU"]
[null,"NA3","DNA3.1","First meeting of eVSAG under auspices of EXPReS",4,"R","PP"]
[null,"NA4","DNA4.02","Creation of EXPReS web-based management tools",4,"O","PP"]
[null,"JRA1","DJ1.4","Correlator design specification",5,"R","PU"]
[null,"JRA1","DJ1.5","Overall design document",6,"R","PU"]
[null,"JRA1","DJ1.6","eVLBI-Grid design document",6,"R","PU"]
[null,"NA4","DNA4.03","Generation of PR material (phase 1) ",6,"O","PU"]
[null,"SA1","DSA1.2","Job preparation utilities",6,"D","PU"]
[null,"SA1","DSA1.3","Fast/adaptive scheduling tools",6,"D","PU"]
[null,"SA2","DSA2.01","Feasibility study of the last-mile connection to the nearest NREN node for participant CNIG-IGN",6,"R","PU","CNIG-IGN"]
[null,"SA2","DSA2.02","Feasibility study of the last-mile connection to the nearest NREN node for participant MPIfR",6,"R","PU","MPIfR"]
[null,"SA2","DSA2.03","Equipment of the last-mile infrastructure for participant INAF (telescope in Medicina)",6,"O","PU","INAF"]
[null,"SA2","DSA2.04","Feasibility study of the last-mile connections to the nearest GEANT NREN node for participant CAS (Shanghai, Urumqi, Miyun, Yunnan )",6,"R","PU","CAS"]
[null,"SA2","DSA2.05","Feasibility study of the last-mile connection to the nearest NREN node for participant VIRAC",6,"R","PU","VIRAC"]
[null,"SA2","DSA2.06","Feasibility study of the last-mile connection to the nearest NREN node for participant HRAO",6,"R","PU","HRAO"]
[null,"SA2","DSA2.07","Feasibility study of the last-mile connection to the nearest NREN node for participant NAIC (Arecibo)",6,"R","PU","NAIC"]
[null,"SA2","DSA2.08 ","Feasibility study of the last-mile connection to the nearest NREN node for participant TIGO",6,"R","PU","TIGO"]
[null,"SA2","DSA2.09","Feasibility study of the last-mile connection to AARNET for participant CSIRO",6,"R","PU","AARNET"]
[null,"JRA1","DJ1.7","eVLBI fringes PC-EVN",7,"D","PU"]
[null,"JRA1","DJ1.8","LOFAR connection strategic document",7,"R","PU"]
[null,"JRA1","DJ1.9","Data acquisition design document",8,"R","PU"]
[null,"SA1","DSA1.4","eMERLIN VSI interfaces design",9,"P","PU"]
[null,"SA1","DSA1.5","Selective data processor controls",9,"D","PU"]
[null,"JRA1","DJ1.10","eVLBI-Grid interface document",10,"R","PU"]
[null,"SA2","DSA2.10","e-VLBI test observations, Medicina",10,"R","PU","INAF"]
[null,"NA1","DNA1.01","Annual report (incl. Financial information) to EC ",12,"R","PP"]
[null,"NA2","DNA2.02","NA2 annual report No. 1 (as part of EXPReS Ann. Rep No. 1)",12,"R","PP"]
[null,"NA4","DNA4.04","e-VLBI Demonstration and attendance at Network events.",12,"O","PU"]
[null,"SA1","DSA1.5","Network Protocol decision",12,"D","PU"]
[null,"SA1","DSA1.7","Monitored information handling modules",12,"D","PU"]
[null,"SA1","DSA1.8","Monitoring processes",12,"D","PU"]
[null,"SA2","DSA2.011","Equipment of the last-mile infrastructure for participant MRO",12,"O","PU","MRO"]
[null,"SA2","DSA2.12","Construction and equipment of the last-mile infrastructure for participant CNIG-IGN",12,"O","PU","CNIG-IGN"]
[null,"SA2","DSA2.13 ","Construction and equipment of the last-mile infrastructure for participant MPIfR",12,"O","PU","MPIfR"]
[null,"JRA1","DJ1.11","Protocols performance report",13,"R","PU"]
[null,"JRA1","DJ1.12","Software correlator core",14,"P","PU"]
[null,"JRA1","DJ1.13","Software data product",15,"P","PU"]
[null,"SA1","DSA1.9","Tests using local Jodrell Bank home e-MERLIN telescope",15,"D","PU"]
[null,"SA1","DSA1.10","Real-time data processor control software",15,"P","PU"]
[null,"NA3","DNA3.2","eVSAG meeting No. 2",16,"R","PP"]
[null,"SA1","DSA1.11","Real-time Pipeline",16,"D","PU"]
[null,"JRA1","DJ1.14","Data acquisition interface document",18,"R","PU"]
[null,"JRA1","DJ1.15","LOFAR station interface report",18,"R","PU"]
[null,"JRA1","DJ1.16","Software for workflow management",18,"P","PU"]
[null,"NA2","DNA2.03","EVN-NREN meeting No. 2 ",18,"R","PP"]
[null,"NA4","DNA4.05 ","Generation of new PR material (phase 2)",18,"O","PU"]
[null,"SA1","DSA1.12","Visibility monitor",18,"D","PU"]
[null,"SA1","DSA1.13","Tested software for operational improvements",18,"D","PU"]
[null,"SA1","DSA1.14","Test using remote e-MERLIN telescope",18,"D","PU"]
[null,"SA1","DSA1.15 ","VSI Interfaces",18,"D","PU"]
[null,"SA1","DSA1.16 ","VSI support software",18,"D","PU"]
[null,"SA2","DSA2.14","10 Gbps link upgrade between MERLIN and JIVE",18,"O","PU","MERLIN, JIVE"]
[null,"SA2","DSA2.15","e-VLBI test observations, Metsahovi",18,"R","PU","MRO"]
[null,"SA2","DSA2.16","Construction and equipment of the last-mile infrastructure for participant Shanghai",18,"O","PU","CAS"]
[null,"SA2","DSA2.17 ","Construction and equipment of the last-mile infrastructure in AARNET to allow connection of participant CSIRO",18,"O","PU","AARNET,CSIRO"]
[null,"SA2","DSA2.18","Construction and equipment of the last-mile infrastructure for participant Urumqi",18,"O","PU","CAS"]
[null,"SA2","DSA2.19 ","Construction and equipment of the last-mile infrastructure for participant Miyun",18,"O","PU","CAS"]
[null,"SA2","DSA2.20 ","Construction and equipment of the last-mile infrastructure for participant Kunming",18,"O","PU","CAS"]
[null,"SA2","DSA2.21 ","Construction and equipment of the last-mile infrastructure for participant VIRAC",18,"O","PU","VIRAC"]
[null,"SA2","DSA2.22 ","Equipment of the last-mile infrastructure for participant NAIC",18,"O","PU","NAIC"]
[null,"SA2","DSA2.23 ","Construction and equipment of the last-mile infrastructure for participant TIGO",18,"O","PU","TIGO"]
[null,"SA2","DSA2.24","AARNET connectivity  enhancements",18,"O ","PU","AARNET"]
[null,"SA2","DSA2.25","Feasibility study of the last-mile connection to the nearest GÉANT node for participant INAF (Sardinia)",20,"R","PU","INAF"]
[null,"SA2","DSA2.26 ","10 Gbps link between UniMan and OSO for ultra-VLBI tests",20,"O","PU","UniMan,OSO"]
[null,"SA1","DSA1.17 ","Flexible local GE network",21,"D","PU"]
[null,"SA2","DSA2.27","e-VLBI test observations, Effelsberg",21,"R","PU","MPIfR"]
[null,"SA2","DSA2.28","e-VLBI test observations, Metsahovi",22,"R","PU","ATNF"]
[null,"SA2","DSA2.29","e-VLBI test observations, Yebes",22,"R","PU","OAN"]
[null,"JRA1","DJ1.17","Software for correlation on cluster",23,"P","PU"]
[null,"JRA1","DJ1.18","Data acquisition test report",23,"R","PU"]
[null,"JRA1","DJ1.19","Data acquisition prototype at telescope",23,"P","PU"]
[null,"JRA1","DJ1.20","Overall broadband demonstration",23,"D","PU"]
[null,"JRA1","DJ1.21","Software cluster correlation",23,"P","PU"]
[null,"JRA1","DJ1.22","First fringes software correlator",23,"D","PU"]
[null,"JRA1","DJ1.23","Software to collect distributed output",24,"P","PU"]
[null,"NA1","DNA1.02","Annual report (incl. Financial information) to EC ",24,"R","PP"]
[null,"NA2","DNA2.04","NA2 annual report No. 2 (as part of EXPReS Ann. Rep No. 2)",24,"R","PP"]
[null,"NA4","DNA4.06 ","e-VLBI Demonstration and attendance at Network events.",24,"O","PU"]
[null,"SA1","DSA1.18","Network monitoring tools",24,"D","PU"]
[null,"SA1","DSA1.19","Multiple e-MERLIN  telescope  tests",24,"D","PU"]
[null,"SA2","DSA2.30 ","Construction and equipment of the last-mile infrastructure for participant HartRAO",24,"O","PU","HRAO"]
[null,"NA2","DNA2.05","EVN-NREN meeting No. 3",26,"R","PP"]
[null,"NA2","DNA2.06","EVN-NREN representatives present EXPReS networking results at the e-VLBI Science & Technology Workshop ",26,"R","PU"]
[null,"NA3","DNA3.3","eVSAG meeting No. 3",26,"R","PP"]
[null,"JRA1","DJ1.24","Software to create data product from distributed correlation ",27,"P","PU"]
[null,"JRA1","DJ1.25","Software routing",29,"P","PU"]
[null,"JRA1","DJ1.26","eMERLIN interface available",30,"P","PU"]
[null,"NA3","DNA3.4","e-VLBI Workshop held in Onsala",30,"O","PU"]
[null,"SA1","DSA1.20 ","Improved network applications",30,"D","PU"]
[null,"SA1","DSA1.21","Monitoring user interfaces",30,"D","PU"]
[null,"SA2","DSA2.31","e-VLBI test observations, Urunqi",30,"R","PU","CAS"]
[null,"SA2","DSA2.32","e-VLBI test observations, Mijun",30,"R","PU","CAS"]
[null,"SA2","DSA2.33","e-VLBI test observations, Kunming",30,"R","PU","CAS"]
[null,"SA2","DSA2.34","e-VLBI test observations, VIRAC",30,"R","PU","VIRAC"]
[null,"SA2","DSA2.35","e-VLBI test observations, HRAO",30,"R","PU","HRAO"]
[null,"SA2","DSA2.36","e-VLBI test observations, NAIC, Arecibo",30,"R","PU","NAIC"]
[null,"SA2","DSA2.37","e-VLBI test observations, TIGO",30,"R","PU","TIGO"]
[null,"SA2","DSA2.38 ","Construction and equipment of the last-mile infrastructure for participant INAF (Sardinia)",30,"O","PU","INAF"]
[null,"JRA1","DJ1.27","Fringes with new routing",31,"D","PU"]
[null,"NA3","DNA3.5","Publication of e-VLBI Workshop proceedings",32,"R","PU"]
[null,"JRA1","DJ1.28 ","Software distributed correlation",33,"P","PU"]
[null,"JRA1","DJ1.29","First fringes Grid correlator",34,"D","PU"]
[null,"JRA1","DJ1.30 ","First fringes on FABRIC",35,"D","PU"]
[null,"JRA1","DJ1.31","Final report",36,"R","PU"]
[null,"NA1","DNA1.03 ","Annual report (incl. Financial information) to EC ",36,"R","PP"]
[null,"NA1","DNA1.04 ","Final Report to Board and EC ",36,"R","PP"]
[null,"NA1","DNA1.05 ","Final Plan for using and disseminating knowledge",36,"R","PP"]
[null,"NA1","DNA1.06","Implementation of the Gender Action Plan",36,"R","PP"]
[null,"NA1","DNA1.07","Raising public participation and awareness ",36,"R","PU"]
[null,"NA2","DNA2.07","NA2 annual & Final reports ",36,"R","PP"]
[null,"NA4","DNA4.07 ","e-VLBI Demonstration and attendance at network events.",36,"O","PU"]

{"sheet":"Milestones- fromsections","index":3,"n_rows":38,"n_cols":7,"rows_kept":38,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
[null,"Milestones"]
[null,"- Taken from each activity's section"]
[]
[null,"Group","Milestone Number (As Listed)","New Milestone Number","Description","Expected Completion","Actual Completion "]
[null,"NA1","MN1.1","M-NA1.1","Conclusion of the Cons. Agreement","month -3 "]
[null,"NA1","MN1.2","M-NA1.2","Appointment of the project manager","month 0"]
[null,"NA1","MN1.3","M-NA1.3","Appointment of the administrative assistant","month 0"]
[null,"NA2","EVN-NREN","M-NA2.1","chair attends EXPReS Board Meeting No. 1","month 2"]
[null,"NA2","EVN-NREN","M-NA2.2","chair attends EXPReS Consortium Board Meeting No. 2","month 14 "]
[null,"NA2","EVN-NREN","M-NA2.3","chair attends EXPReS Board Meeting No. 3","month 26 "]
[null,"NA3","EVSAG ","M-NA3.1","chair attends EXPReS Consortium Board Meeting ","month 2"]
[null,"NA3","EVSAG ","M-NA3.2","chair attends EXPReS Consortium Board Meeting ","month 14"]
[null,"NA3","EVSAG ","M-NA3.3","chair attends EXPReS Consortium Board Meeting ","month 26"]
[null,"NA4","NA4.i","M-NA4.1","The EXPReS web-site goes public and on-line;","not listed"]
[null,"NA4","NA4.ii","M-NA4.2","Management tools are added to the web-site and used effectively for Project management; ","not listed"]
[null,"NA4","NA4.iii","M-NA4.3","the first PR material is produced and presented at the first iGRID networking event; ","not listed"]
[null,"NA4","NA4.iv","M-NA4.4","EXPReS participates in annual public open-days at JIVE and the other partner institutes involved in such outreach activities;  ","not listed"]
[null,"NA4","NA4.v","M-NA4.5","Press release announcing the EXPReS e-VLBI facility as an open, production-level facility open to all astronomers. Other milestones include: the appointment of the EXPReS Outreach Officer. ","not listed"]
[null,"SA1","MSA1.1","M-SA1.1","Call for Proposals for e-VLBI service ",1]
[null,"SA1","MSA1.2","M-SA1.2","Preliminary e-VLBI Service            ",4]
[null,"SA1","MSA1.3","M-SA1.3","Basic data-link technology ",6]
[null,"SA1","MSA1.4","M-SA1.4","Basic VLBI elements adapted for e-VLBI",6]
[null,"SA1","MSA1.5","M-SA1.5","Enhanced ToO support",17]
[null,"SA1","MSA1.6","M-SA1.6","Enhanced e-VLBI Service",18]
[null,"SA1","MSA1.7","M-SA1.7","Enhanced ToO support",22]
[null,"SA1","MSA1.8","M-SA1.8","Adaptive network utilization",22]
[null,"SA1","MSA1.6b","M-SA1.9","Full bandwidth utilization (duplicate number)",24]
[null,"SA1","MSA1.7b","M-SA1.10","Live e-VLBI system monitoring (duplicate number)",24]
[null,"SA1","MSA1.8b","M-SA1.11","Full e-VLBI Service (duplicate number)",24]
[null,"SA2","M1:","M-SA2.1","Feasibility study of the last-mile connection to the nearest GÉANT node.","To + 6 months."]
[null,"SA2","M2:","M-SA2.2","Construction and equipment of the last-mile infrastructure.","To + 18 months."]
[null,"SA2","M3:","M-SA2.3","e-VLBI Fringes (Detection).","To +10 months. "]
[null,"JRA1","DJ1.1","M-JRA1.1","Requirements document data acquisition","not listed"]
[null,"JRA1","DJ1.2","M-JRA1.2","Strategic document broadband protocols","not listed"]
[null,"JRA1","DJ1.4","M-JRA1.3","Design document correlator algorithms","not listed"]
[null,"JRA1","DJ1.6","M-JRA1.4","eVLBI - Grid design document","not listed"]
[null,"JRA1","DJ1.5","M-JRA1.5","overall design document DJ1.5, which will describe all the interfaces in the project.","Not listed"]