Technical Annex 1: Second Period Plan

1.  Implementation Plan

1.1  Management Activity

1.1.1  NA1: Management of I3

The 18 month plan (project month 13 to 31) for NA1 contains no radical changes or deviations from the original plan.  No new deliverables have been added.  The deliverable in the first 12 months for NA1 is this annual report.  All milestones identified in the first 18 month plan have been addressed and no new milestones will be added.

There are several administrative elements to address.  Each is detailed below with references to other sections of this report as several of the changes require longer supporting documentation.

- Change in Project Coordinator

Through the monthly reports, the EC. was notified of the change from Mike Garrett to Huib Jan van Langevelde.  Through email discussions with EXPReS’s new Science Officer Jean-Luc Dorel, the project office was informed that the notification in the monthly report was sufficient to initiate the formal changes necessary from the EC.’s point of view.  However, the project office was asked to submit a C.V. for van Langevelde.  The full document is included as an appendix in Section E.

- Addendum to the Consortium Agreement

The EXPReS Board discussed and agreed upon an addendum to the Consortium Agreement.  The formal changes were distributed to our partners and all have signed and returned the document.  The full text of the document is included as an appendix in Section E.

- Errors in initial "A Forms"

Early in the project, Michael Garrett notified our Science Officer that the amount of funding received for the first 18 months was larger than expected.  The inconsistencies resulted from differences in the A Forms.  At that time, the advice was to proceed with the project and correct the inconsistencies during the Annual Review.

Project communications were using the 18 month distribution as outlined in "Table 3 - Summary table of expected budget and of the Community contribution requested to 18 months" in Annex 1 Description of Work and consistent with A3.3.  The total requested EC contribution for the first 18 months was expected to be 1,201,200 EUR.  This is the figure that was used when funds were distributed to our partners.

A3.1 and A3.2 indicate that the total Requested EC. Contribution for the three years of the project is 3,900,000 EUR.  Using the quantities listed, the 18 month distribution is 1,850,000 EUR.  This sum is inconsistent with the amount in the A3.3 and Table 3.

The Project Office received 1,572,000 EUR to be distributed to the partners.  The distribution of funding followed the figures listed in Table 3 and Form A3.3.  The remaining funds and next distribution take into account the inconsistencies.

- Errors in initial Deliverables and Milestone tables

The Project Office noted to our Science Officer some typographical errors and inconsistencies in the Deliverables and Milestone tables early in the project.  The errors were generally small and did not involve major activities in the first 12 months of the project.  The recommendation was to identify these items in the First Annual Report and correct the tables as appropriate.  The tables have been identified in the historical review and are corrected in the next 18 month plan per activity.

These difficulties may be a result of the large number of deliverables and their organization.  The project considered combining deliverables to consolidate their presentation, but this initial exercise proved more confusing for the regular operation of the project.  The project office will continue to seek ways to clarify the organization of the deliverables and will consolidate deliverables as applicable and appropriate for the next review.  The project office will continue to track and identify deliverables that are past due using the project wiki and direct communication techniques.

- Unexpected Travel Costs

Over the first year, we learned a bit about the financial spending for our partners.  One of the items we will need to address is the radically different cost of travel for our international partners.  Specifically, the cost for our Chilean and Australian partners are particularly difficult.  Both have been active in the project with Australia providing the Vice-Chair for our Board.  In order to improve participation, we continue to schedule EXPReS meetings near other meetings that will draw our partners.  We hope to provide some additional funding for our more distant partners.

The project office will investigate the use of existing video conferencing technologies as a supplement to existing meetings.  While the tools and technologies have matured considerably over the past few years, none of them have been able to address the time zone problem that effects all globally distributed projects.  The project office will work to determine if video and related collaborative tools can naturally integrate into existing communications systems and will also compare with the experience of other projects.

1.1.1.1  NA1: Deliverables and Milestones Tables

Deliverables for the remainder of the project (months 13-36).  NA1 has completed all milestones listed in the DOW and does not plan to add any additional.

| D# | AD# | Deliverable Description | Lead | Delivery month | Status |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Planned | Actual |  |
| D81 | NA1.02 | Annual report (incl. Financial information) to EC | JIVE | 24 |  |  |
| D111 | NA1.03 | Annual report (incl. Financial information) to EC | JIVE | 36 |  |  |
| D112 | NA1.04 | Final Report to Board and EC | JIVE | 36 |  |  |
| D113 | NA1.05 | Final Plan for using and disseminating knowledge | JIVE | 36 |  |  |
| D114 | NA1.06 | Implementation of the Gender Action Plan | JIVE | 36 |  |  |
| D115 | NA1.07 | Raising public participation and awareness | JIVE | 36 |  |  |

1.1.1.2  NA1: Period 2 Distribution

| P # | Short Name | Period 2 Requested Distribution |
| --- | --- | --- |
| 1 | JIVE | 106,575 € |
| 2 | AARNET | 1,575 € |
| 3 | DANTE | 2,775 € |
| 4 | PSNC | 1,575 € |
| 5 | SURFnet | 1,575 € |
| 6 | ASTRON | 1,575 € |
| 7 | CNIG-IGN | 1,575 € |
| 8 | CSIRO | 1,575 € |
| 9 | NRF | 1,575 € |
| 10 | INAF | 1,575 € |
| 11 | MPG | 1,575 € |
| 12 | TKK | 1,575 € |
| 13 | CORNELL | 1,575 € |
| 14 | UMK | 1,575 € |
| 15 | OSO | 2,400 € |
| 16 | SHAO | 1,575 € |
| 17 | UDEC | 1,725 € |
| 18 | UNIMAN | 1,725 € |
| 19 | VeA/VIRAC | 1,725 € |

1.2  Networking Activity

1.2.1  NA2: EVN-NREN Forum

1.2.1.1  NA2: Deliverables and Milestones Table

Several minor errors were identified in the NA2 Deliverables.  The errors and corrections are noted as:

•	D82 is given activity deliverable number NA2.08.  No number was associated

•	D82 is listed as support for Annual Report 2 and should be listed as support for Annual Report 3.  The description and planned delivery month are modified to reflect the changes.

•	Activity D90 is given AD# NA2.09.  Activity D90 is then immediately removed as it is redundant with D88.

•	D31, D82 The lead for the annual report activity is identified as DANTE, the leader of the activity.  Note that the overall responsibility for the Annual Report remains as a deliverable under JIVE.

As EXPReS matures, there will be increased need for strong ties between the different network engineering groups.  The EVN-NREN forum will work to increase the communication between the networking communities in astronomy and infrastructure through additional meetings and an expansion of the EVN-NREN mailing list.  Through this type of forum, issues can be identified and addressed between established contact points.

The table below shows the errors in red with the corrections.  D90 will remain in the table, but struck-out to indicate its cancellation.

| D# | AD# | Deliverable Description | Lead | Delivery month | Status |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Planned | Actual |  |
| D48 | NA2.03 | EVN-NREN meeting No. 2 | JIVE | 18 |  |  |
| D31 | NA2.04 | NA2 annual report No. 2 (as part of EXPReS Ann. Rep No. 2) | DANTE | 24 |  |  |
| D82 | NA2.08 | NA2 annual report No. 3 (as part of EXPReS Ann. Rep No. 3) | DANTE | 36 |  |  |
| D88 | NA2.05 | EVN-NREN meeting No. 3 | DANTE | 26 |  |  |
| D89 | NA2.06 | EVN-NREN representatives present EXPReS networking results at the e-VLBI Science & Technology Workshop | DANTE | 26 |  |  |
| D90 | NA2.09 | EVN-NREN meeting | DANTE | n/a | n/a | n/a |
| D116 | NA2.07 | NA2 annual & Final reports | JIVE | 36 |  |  |

No changes are planned for the Milestones table.

| M# | AM# | Milestones Description | Lead | Delivery month | Status |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Planned | Actual |  |
| M4 | MN2.1 | EVN-NREN chair attends EXPReS Board Meeting No. 1 | DANTE | 2 | 6 | complete |
| M5 | MN2.2 | EVN-NREN chair attends EXPReS Consortium Board Meeting No. 2 | DANTE | 14 |  |  |
| M6 | MN2.3 | EVN-NREN chair attends EXPReS Board Meeting No. 3 | DANTE | 26 |  |  |

1.2.1.2  NA2: Period 2 Distribution

| P # | Short Name | Period 2 Requested Distribution |
| --- | --- | --- |
| 1 | JIVE | 14,475 € |
| 2 | AARNET | 2,100 € |
| 3 | DANTE | 6,075 € |
| 4 | PSNC | 1,350 € |
| 5 | SURFnet | 1,350 € |
| 6 | ASTRON | 818 € |
| 7 | CNIG-IGN | 825 € |
| 8 | CSIRO | 1,500 € |
| 9 | NRF | 1,500 € |
| 10 | INAF | 825 € |
| 11 | MPG | 825 € |
| 12 | TKK | 825 € |
| 13 | CORNELL | 1,500 € |
| 14 | UMK | 825 € |
| 15 | OSO | 825 € |
| 16 | SHAO | 1,500 € |
| 17 | UDEC | 1,650 € |
| 18 | UNIMAN | 825 € |
| 19 | VeA/VIRAC | 827 € |

1.2.2  NA3: e-VLBI Science Forum

Within NA3 the eVSAG (e-VLBI Science Advisory Group) will remain an active form for discussing policy to promote end-user science with the e-VLBI infrastructure.  In the first year e-VLBI as been organized with one 24hr session every 5 weeks in between the EVN’s disk based runs.  Proposed observations for e-VLBI on these fixed dates are submitted 2 weeks before the observation date and are evaluated by the EVN PC.  It is expected that  this system will evolve in two ways:

1) 	In 2008 when the capability of e-VLBI will equal or exceed disk based VLBI it is possible that e-VLBI will replace a significant part of the disk based observations in the standard EVN sessions.  In addition for time variable ‘targets of opportunity’ we will investigate moving to a system when e-VLBI runs can be set up at short (few days) notice

2) 	In the second half of 2007, where e-VLBI is still on fixed dates which are scheduled well in advance, we are planning to enhance the capabilities for science via a new proposal mechanism.

Within the eVSAG, a sub-group has been set up to investigate options within point 1 for e-VLBI use in 2008 (to be reported and discussed at the next eVSAG face-to-face meeting in June 2007).

Under the second point above there is extensive eVSAG discussions ongoing by email on an improved proposal system for e-VLBI; a final policy approved by the PC will be in place by early May when the next regular EVN call for proposals goes out.  The essence of e-VLBI is speed and the challenge is to design a proposal system which allows users rapid access to new unpredicted and rapidly changing astronomical events while still ensuring a high scientific standard via peer-review.  At present the discussion centers on allowing a new class of ‘triggered’ proposals.  These proposals would be submitted for the usual EVN deadlines of 1st February, 1st June and 1st October and would be fully reviewed and rated by the EVN program committee.  The proposals would contain a list of potential target sources together with a proposed ‘trigger’ criteria (perhaps becoming brighter than a certain level in radio monitoring with other telescopes or an X-ray flare occurring).  Approved projects in this class would be activated if a trigger request with supporting evidence is submitted and approved by the PC chair up to three days before the e-VLBI run.  In addition to this class of observations another class of general, non-time critical observations would be created which could be submitted by the normal deadlines.  Observations in this class will be observed if no higher rated triggered proposals occur.  Finally there would be mechanisms available for ‘quick look’ calibrator observations and to enable totally unpredicted (i.e., no source positions known beforehand), very high priority observations to be observed in e-VLBI runs if they occur just before a scheduled observing opportunity.

1.2.2.1  NA3: Deliverables and Milestones Table

The next deliverable is the 3rd face to face meeting which is expected to be on time and be held in mid-June (perhaps connected to the EVN PC’s next meeting).  In the revised plan below the e-VLBI science workshop has (relative to the original DOW) been moved one month later (till October 2008) because of teaching commitments of the main organizer (eVSAG chair -John Conway).  This will cause a one month shift in the date of publications form this workshop.

A minor error was identified in the original deliverables table with D94 lacking a Lead.  OSO has been identified and added.

| D# | AD# | Deliverable Description | Lead | Delivery month | Status |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Planned | Actual |  |
| D46 | NA3.2 | eVSAG meeting No. 2 | OSO | 16 |  |  |
| D91 | NA3.3 | eVSAG meeting No. 3 | OSO | 26 |  |  |
| D94 | NA3.4 | e-VLBI Workshop held in Onsala | OSO | 31 |  |  |
| D107 | NA3.5 | Publication of e-VLBI Workshop proceedings | OSO | 32 |  |  |

The eVSAG chair will continue to play an active role in informing the rest of the project of the views of the committee (and keep abreast of developments in other parts of the project). He will attend all future meetings of the EXPReS board (and most likely all meeting of the ECN board).

No changes are planned for the Milestones table.

| M# | AM# | Milestones Description | Lead | Delivery month | Status |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Planned | Actual |  |
| M8 | MN3.2 | eVSAG chair attends EXPReS Consortium Board Meeting | DANTE | 14 |  |  |
| M9 | MN3.3 | eVSAG chair attends EXPReS Consortium Board Meeting | DANTE | 26 |  |  |

1.2.2.2  NA3: Period 2 Distribution

| P # | Short Name | Period 2 Requested Distribution |
| --- | --- | --- |
| 1 | JIVE | 9,300 € |
| 2 | AARNET | 0 € |
| 3 | DANTE | 0 € |
| 4 | PSNC | 0 € |
| 5 | SURFnet | 0 € |
| 6 | ASTRON | 1,200 € |
| 7 | CNIG-IGN | 1,200 € |
| 8 | CSIRO | 2,250 € |
| 9 | NRF | 2,250 € |
| 10 | INAF | 1,200 € |
| 11 | MPG | 1,200 € |
| 12 | TKK | 1,200 € |
| 13 | CORNELL | 2,250 € |
| 14 | UMK | 1,200 € |
| 15 | OSO | 7,200 € |
| 16 | SHAO | 2,250 € |
| 17 | UDEC | 2,250 € |
| 18 | UNIMAN | 1,200 € |
| 19 | VeA/VIRAC | 1,200 € |

1.2.3  NA4: E-VLBI Outreach, Dissemination & Communication

1.2.3.1  NA4: Deliverables and Milestones Table

Over the next 12 months, we will move the focus from internal to external elements, focusing on helping disseminate scientific work completed using EXPReS.  In addition to planned dissemination material, the project will consider ways to leverage scientific results of e-VLBI in addition to the current

As mentioned previously, NA4 milestones for the first 12 months were modified.  Their planned due date was changed from a fixed date to an "ongoing activity" to reflect the true nature of the deliverable.  Those deliverables are D10 and D34.  For upcoming deliverables:

•	D49 will maintain its focus on a display stand and will not be assumed to be an ongoing deliverable.

In addition, a few minor changes are identified for the deliverable and milestone tables.

•	D49 will have JBO as the lead.  This is a result of maternity leave for the public outreach officer and the official delegation of the task to Alastair Gunn at JBO/Manchester.

•	D83 did not have an associated lead.  JIVE is identified as the primary, but close cooperation with DANTE will continue to focus on the Network-centric events

| D# | AD# | Deliverable Description | Lead | Delivery month | Status |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Planned | Actual |  |
| D49 | NA4.05 | Generation of new PR material (phase 2) | JBO | 18 |  |  |
| D83 | NA4.06 | e-VLBI Demonstration and attendance at Network events. | JIVE | 24 |  |  |
| D117 | NA4.07 | e-VLBI Demonstration and attendance at network events. | JIVE | 36 |  |  |

The remaining milestone for NA4 is listed below.  Note that in the Description of Work, due dates were not identified.  The M14 press release is expected at the end of the project and is listed as such.

| M# | AM# | Milestones Description | Lead | Delivery month | Status |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Planned | Actual |  |
| M14 | MN4.5 | Press release announcing the EXPReS e-VLBI facility as an open, production-level facility open to all astronomers. Other milestones include: the appointment of the EXPReS Outreach Officer | JIVE | 36 |  |  |

1.2.3.2  NA4: Period 2 Distribution

| P # | Short Name | Period 2 Requested Distribution |
| --- | --- | --- |
| 1 | JIVE | 90,675 € |
| 2 | AARNET | 0 € |
| 3 | DANTE | 0 € |
| 4 | PSNC | 0 € |
| 5 | SURFnet | 0 € |
| 6 | ASTRON | 0 € |
| 7 | CNIG-IGN | 0 € |
| 8 | CSIRO | 0 € |
| 9 | NRF | 0 € |
| 10 | INAF | 0 € |
| 11 | MPG | 0 € |
| 12 | TKK | 0 € |
| 13 | CORNELL | 0 € |
| 14 | UMK | 0 € |
| 15 | OSO | 0 € |
| 16 | SHAO | 0 € |
| 17 | UDEC | 0 € |
| 18 | UNIMAN | 20,625 € |
| 19 | VeA/VIRAC | 0 € |

1.3  Service Activities

1.3.1  SA1: Production e-VLBI Services

1.3.1.1  SA1: General Comments

Several factors have influenced the order in which work packages were tackled during the first year.

1.	The difficulty in finding suitable candidates unavoidably caused delays.

2.	Early on in the project we realized that the original plan did not sufficiently take the complexity of the correlator system into account.  Because of this we decided to start the software engineers off on some specific well-defined elements of the work packages to give them a chance to familiarize themselves with the system.

3.	In order to be able to offer an e-VLBI service to the astronomical community from the very first day of the EXPReS project on, we had to have an operational system in place. For this, a number of rigorous modifications to the control system had to be made by the regular JIVE staff, in part before the actual start of the EXPReS project.

As a result of this, several deliverables have been produced that were not due for many months, while other deliverables were delayed. But although the order of deliverables may have been altered, the project as a whole is well on schedule. Changes to the timeline will be addressed in the plan for the next 18 months. First we will concentrate on the delayed deliverables.

It should be noted that D35 and D28 were both numbered as DSA1.5 in the original EXPReS Description of Work (page 102). Judging from the accompanying GANTT chart and the description of the work packages it seems clear that the planned delivery months were swapped as well. In the deliverables table in this section the numbering has been corrected accordingly.

The service provided to astronomers continues to evolve and improve.  The need for new tools is recognized and many of these tools fall into existing deliverables and activities.  The Cactii tools installed at JIVE help track the status of network connections and are the first stage in a more complete set of network monitoring tools to be delivered as part of SA1.18.  These network monitoring tools will work in conjunction with current investigations into related efforts to assist in network quality.  For example, PSNC has investigated the use of QOS as a possible tool for data transport across their current connection to GEANT.

1.3.1.2 Delayed deliverables

•	SA1.2: Job preparation utilities

This is one of the deliverables that had to be delayed until our new software engineers were sufficiently up to speed to tackle it. The work package summary lists 1) the purging of utilities of non-relevant actions, and 2) optimization for real-time case. Much work has been spent on timing the system and identifying delays (http://www.jive.nl/~jive_cc/sin/sin9.pdf), which has already led to a considerable improvement in its real-time behavior by cutting down on start-up and configuration times. Some additional work is still in progress. The work package description further mentions purging utilities from irrelevant functions concerned with magnetic media, and changing the data entry path. At this point, it does not seem likely that this will actually happen. Magnetic media are bound to be used for some time yet, and the EVN telescopes do not only participate in astronomical observations, but are also part of geodetic VLBI arrays. It does not seem feasible (or advisable), to one-sidedly change the way observations are scheduled. Rationalizing and streamlining the current scheduling process will be far more efficient.

•	SA1.3: Fast/adaptive scheduling tools

Work on this deliverable had to be postponed as well to allow our new software engineers to familiarize themselves with the intricacies of VLBI. The first element, a field system based daemon, has been created, and further development will continue depending on the availability of field systems and test time.

•	SA1.4: eMERLIN VSI interfaces design

This deliverable was partly fulfilled (http://www.jive.nl/dokuwiki/doku.php/fabric:wp1), but further development awaits the delivery of various parts of hardware. A detailed description of the status of SA1.4 is to be found in section 1.5.1.2.2 of this document.

•	SA1.5: Network protocol decision

A lot of work has been done on network protocol research over the past years, both at JIVE and at the University of Manchester. A final decision however cannot be made until a number of hard- and software developments come together. Serious testing with different transport protocols at high data rates will only be possible when the Mark5A hardware upgrade is finished, and when the Mark5A software, developed and maintained at Haystack Observatory, has been upgraded to reliably function under new Linux kernels.

•	SA1.7: Monitored information handling modules

Work on this package was delayed until most of the hardware changes have taken place, as the amount and nature of monitoring information will depend to some degree on the available hardware.  It is not clear at this point of the project if it will be useful to store the monitoring information at all, and if a simple SQL database will not be sufficient.

1.3.1.3 Accelerated deliverables

•	SA1.10: Real-time data processor control software

Completion of this deliverable was an absolute pre-condition for offering an e-VLBI service to the astronomical community. Work was started well before the EXPReS software engineers were hired, in fact even before the start of the project itself, and consisted of a rigorous re-writing of large parts of the correlator control code.

•	SA1.11: Real-time pipeline, SA1.12: Visibility monitor

The real-time pipeline and the visibility monitor were perfect projects for the new software engineers to familiarize themselves with the correlator system and data format issues.

•	SA1.15: VSI Interfaces

The move to VSI interfaces involves a variety of hardware components that had to be designed, ordered and produced at different locations. Serial links were manufactured at ASTRON in Dwingeloo and MPIfR at Bonn, Correlator Interface Boards at Haystack Observatory and Mark5B upgrade kits at Conduant, USA.

•	SA1.17: Flexible local GE network

The expansion of the connectivity of JIVE to SURFnet needed to connect more telescopes to JIVE both through dedicated lightpaths and an IP routed connection forced us to move this deliverable forward.

•	SA1.21: Monitoring user interfaces

This deliverable was treated as an integral part of SA1.7.

1.3.1.2  SA1: Workpackage Summary

The following table is roughly identical to table SA1.1: Work Package Summary, in the EXPReS Annex 1 – “description of work” (page 88).  Finished deliverables have been removed, and the deliverable numbers (both project specific and general) have been added. The yellow entries are newly defined deliverables, the blue entries denote outsourced FTEs (under a contract with Haystack Observatory).  Testing, as listed in the original table, is omitted from the table, as is WP7 (e-VLBI tests and demonstrations). Tests are being run nearly continuously, and demonstrations and science runs are scheduled and organized by the e-VLBI support scientist, as part of his general tasks (increasing awareness of e-VLBI in the astronomical community, researching new applications, supporting e-VLBI observers, testing of new capabilities, scheduling, and general outreach).

| Work Package | D# | AD# | Objectives | FTE | Deliverable |
| --- | --- | --- | --- | --- | --- |
| WP1: Operational Improvements for e-VLBI | Revise and augment observation/correlation software and associated utilities for real-time operation |
| 1.1 Job preparation utilities | D11 | SA1.2 | Purge utilities of non-relevant actions Optimize for real-time case | 0.2 | Real-time data processor control software |
| 1.4 Use of WSRT synthesis data for e-VLBI calibration |  |  | Absolute flux calibration using WSRT synthesis data, obtained in parallel to phased array output | 0.4 | WSRT data processing pipeline |
| 1.5 Space craft tracking correlator mode |  |  | Create correlator operating mode allowing rapid switching between real-time observations of calibrators and disk recording at JIVE, for subsequent processing on software correlator | 0.1 | Operational space craft tracking mode |
| 1.6 On-the-fly fringe fitting |  |  | Perform fringe fitting on the fly, to improve rapid detection of faint sources | 0.1 | Fringe-fitting tool |
| 1.7 Mark5A code modifications |  |  | Modifications to Mark5A code to support e-VLBI with new Linux kernels | 0.1 | Mark5A code modifications |
| 1.8 Mark5B code modifications |  |  | Modifications to Mark5B code to support e-VLBI and compatibility with 64 BOCF operations | 0.2 | Mark5B code modifications |
| 1.9 Automated correlator diagnostics |  |  | Create a tool that monitors all available system diagnostics and automatically issues specific fault warnings | 0.4 | Diagnostic tool |
| 1.10 Removing/adding stations from the correlation process on the fly |  |  | Modify control code to allow removing and adding stations to a running correlator job without the need of a re-start | 0.1 | Modified control code |
| WP2: Data transmission developments | Actions to improve the data rate and robustness of e-VLBI data transfers across the R&E networks |
| 2.2 Application layer improvements | D95 | SA1.20 | Re-arrange mapping of data to enable full use of available network bandwidth | 0.2 | Improved network applications |
| 2.3 Transport protocol evaluation and selection | D28 | SA1.5 | Determine which of the available protocols is optimum for e-VLBI | 0.2 | Protocol decision |
| 2.4 Network monitoring | D84 | SA1.18 | -Deploy monitoring clients across the network -Prepare tools for integration and presentations of network status information -Devise and implement strategies for optimum network utilization | 0.6 | Network monitoring tools |
| 2.6 Investigating a 1024M sub-array |  |  | Investigate the possibility to connect up to 5 telescopes at >1Gbps in order to enable full 1024Mbps e-VLBI | 0.1 | Feasibility report |
| WP3: Target of Opportunity Support | Facilitate and allow dynamic scheduling of the observation |
| 3.2 Fast/adaptive re-scheduling | D12 | SA1.3 | Enable rapid and selective revision of observational objectives and parameters | 0.9 | Fast/adaptive scheduling tools |
| 3.6 Enhancements & additions to real-time pipeline |  |  | Modifications based on user requests and operational considerations | 0.4 | Improved functionality of real-time pipeline |
| 3.7 Real-time download and extraction of station information |  |  | Download station log files as they are written and extract both instantaneous telescope status and calibration information | 0.2 | Real-time station information display and calibration tools |
| WP4: Real-time monitoring functions | Provide feedback to telescopes and data processor enabling operators to achieve optimal performance and to isolate and correct faults during the observation |
| 4.2 Information handling | D36 | SA1.7 | Collection, manipulation and storage of information | 0.2 | Monitored information handling modules |
| 4.5 Enhancements & additions to existing monitoring tools |  |  | Modifications based on user requests and operational considerations | 0.4 | Improved functionality of monitoring tools |
| WP5: Data processor upgrades | Data processor hardware upgrades to remove redundant, tape-media specific elements and otherwise optimize infrastructure for e-VLBI |
| 5.1 VSI hardware changes | D54 | SA1.15 | Upgrade disk/network interface to VSI standard | 0.3 | VSI interfaces |
| 5.2 VSI software changes | D53 | SA1.16 | Adjust correlator control software to operate in VSI hardware environment | 0.9 | VSI support software |
| 5.3 Flexible local GE network | D71 | SA1.17 | To allow flexible data processor/telescope mapping | 0.2 | Flexible local GE network |
| 5.5 Mark5 hardware upgrade |  |  | Complete upgrade of Mark5 hardware (such as motherboards, memory, power supplies) | 0.2 | Upgraded Mark5 units |
| WP6: addition of MERLIN telescopes | e-MERLIN enhancements enabling MERLIN telescopes to be added transparently to the e-VLBI array |
| 6.1: e-MERLIN VSI interfaces | D27 | SA1.4 | Provide direct digital output from multiple e-MERLIN telescopes for transmission to JIVE using VSI protocol | 0.9 | e-MERLIN VSI interfaces |

The focus of SA1 for the next 18 months will be on

1.	adaptive scheduling

2.	conversion of the Mark5A to Mark5B VSI-compatible units

3.	increasing the operational data rate

4.	improving the flexibility and robustness of the correlation process.

Of course, there is a considerable overlap in the work needed to obtain these goals. As can be seen in the previous table, quite a few new deliverables have been defined. During the first year we found that some deliverables required less effort than had been estimated, and that several others had been severely underestimated. Through running an actual e-VLBI service we also became aware of some important features that were missing from the original project plan. But, mainly because of the work effort put into the EXPReS project by the regular JIVE staff, we still have sufficient time and manpower left in the project to address these issues.

1.3.1.2.1 Outsourcing

Part of the work (0.5 FTE) was outsourced to Haystack Observatory. There are a number of reasons for this.

The Mark5 recording/playback system is based on off-the-shelf PC technology, combined with proprietary soft- and hardware from Conduant, the company that manufactures these units. Control code development and maintenance are done at Haystack Observatory, who also handles the contacts with Conduant.

Specific JIVE-related changes to the Mark5 control software are sometimes implemented by JIVE staff, after which they are communicated to Haystack and included in the "official" release. Large modifications however could easily lead to a split into supported and non-supported code versions, which, due to the international nature of VLBI, would be a very bad development. Moreover, the lack of direct access to Conduant would make it cumbersome to request or respond to upgrades in proprietary software libraries. Direct involvement of Haystack software engineers is essential to guarantee an effective and speedy implementation of modifications and bug fixes. Other modifications required by JIVE involve Haystack-developed FPGA code. There is no FPGA programming expertise at JIVE, and while it would certainly be possible to train one of the staff members, the learning curve is steep. Besides, the acquired skills would only be applicable for a very limited purpose. Another option would be to hire a local contractor, who then would face a learning curve in radio astronomy. Outsourcing this work to the people who actually designed the system was felt to be by far the most time-efficient solution.

1.3.1.2.2 Modifications of existing deliverables

The most important changes are to WP3.2: fast/adaptive rescheduling and to WP5.2: VSI software changes. Both packages are very important for the development of e-VLBI and both involve far more effort than originally estimated.

Adaptive scheduling is crucial to transform the EVN into a truly flexible instrument, capable of reacting to transient events on a time-scale of hours. But it also involves building a system enabling remote control of widely different telescope control systems while safeguarding local operational constraints.

VSI software changes will allow JIVE to phase out the Station Units, the main cause of operational instability, and at the same time enable seamless inclusion of other VSI-compliant telescopes. This will however involve a major re-write of the correlator control code.

1.3.1.2.2 Specifics of new deliverables

WP1.4: Use of WSRT synthesis data for e-VLBI calibration.  This work package has been described in some detail in section 1.5.1.1.5 (Software developments at JIVE). It will provide immediate access to WSRT synthesis data (recorded simultaneously with the phased array output) and be of great value both for calibration and for target selection.

WP1.5: Space craft tracking correlator mode. This mode will allow rapid switching between real-time correlation of calibrator sources and recording streaming data on disk packs at JIVE, for later correlation with a purpose-built software correlator, with the spectral resolution needed for this type of observations.

WP1.6: On-the-fly fringe fitting.  Fringe fitting is currently done after correlation. Doing it on-the-fly, with an improved algorithm, and immediately updating the delay polynomials (which will be possible once the Mark5A units have been upgraded to Mark5B) will greatly speed up the calibration process, but also improve the rapid detection of astronomical objects.

WP1.7: Mark5A code modifications. This package has been outsourced to Haystack Observatory. It includes modifications to the current Mark5A control code to enable reliable e-VLBI operations with new Linux kernels, thereby opening the possibility of switching between modified TCP stacks for more efficient data transport.

WP1.8: Mark5B code modifications. This package too has been outsourced to Haystack Observatory. It includes e-VLBI related modifications to the new Mark5B station and correlator control code, and changes for compatibility with JIVE-specific correlator modes.

WP1.9: Automated correlator diagnostics. Due to the complexity of the system, the correlation process can go wrong in many different and often obscure ways. In e-VLBI the time involved with tracking down the exact cause of a problem leads to irretrievable and unacceptable data loss. This work package will create a tool that gathers all diagnostic information produced by the various components of the system and generates a general alarm when anything goes wrong. The monitoring information will make it possible to provide a specific description of the problem at hand. This will greatly simplify trouble shooting and increase the operational efficiency of the system.

WP1.10: Removing/adding stations from the correlation process on the fly. When the transmission from one of the stations fails, for any reason (local correlator or local station problems, network problems), as a rule the station will have to be disconnected from the correlation job. After trouble shooting one can only reconnect this station by restarting the entire job, causing unnecessary loss of data. This work package will modify the control code to enable on-the-fly reconnecting of stations during correlation possible.

WP2.6: Investigating a 1024M sub-array. The EVN can operate at a maximum data rate of 1 Gbps per telescope. This data rate however cannot be accommodated by 1 Gbps networking technology because of the overhead involved (e.g. IP headers), currently limiting the maximum e-VLBI data rate to 512 Mbps. FABRIC, the EXPReS JRA1, deals with high-speed astronomical data transmission and will need a 4 to 10 Gbps connection between the radio telescope at Onsala (Sweden) and the e-MERLIN correlator at Jodrell Bank Observatory (UK). This high-speed connection very probably will pass through SURFnet, as will the planned 10 Gbps connection from Effelsberg (Germany). We want to investigate the use of these connections to stream 1024 Mbps of astronomical data from a few telescopes to JIVE. The WSRT at Westerbork (the Netherlands) could be added as well, by upgrading the current equipment to 10 Gbps. In this way it might be possible to provide a sub-array of some of the most sensitive telescopes of the EVN at the full possible bandwidth.

WP3.6: Enhancements & additions to real-time pipeline. This work package will deal with user- and technology driven modifications during the course of the project.

WP3.7: Real-time download and extraction of station information. Currently, all station-related information is written to log files at the stations, transferred to a central database after the observations and downloaded to JIVE for processing. A real-time download of these log files will provide not only status information but also system temperatures that can be used for immediate amplitude calibration.

WP4.5: Enhancements & additions to existing monitoring tools. Like WP3.6, this work package will deal with user- and technology driven modifications.

WP5.5: Mark5 hardware upgrade. To support the upgrade of Mark5A to B and improve data transmissions during e-VLBI, the outdated hardware in the Mark5 units has to brought up to speed. New motherboards, CPUs and power supplies are being purchased and will be installed during the coming months.

1.3.1.3 SA1: Deliverables and Milestones Table

Yellow entries in the deliverable table denote the newly defined deliverables. O/S stands for outsourced, as described in the report.

| D# | AD# | Deliverable Description | Lead | Delivery month | Status |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Planned | Actual |  |
| D11 | SA1.2 | Job preparation utilities | JIVE | 16 |  | 2 |
|  |  | Mark5 hardware upgrade | JIVE | 16 |  |  |
| D28 | SA1.5 | Network protocol decision | JIVE | 16 |  | 2 |
|  |  | Use of WSRT synthesis data for e-VLBI calibration | JIVE | 17 |  |  |
|  |  | Mark5A code modifications | O/S | 17 |  |  |
|  |  | Mark5B code modifications | O/S | 17 |  |  |
| D95 | SA1.20 | Improved network applications | O/S | 17 |  |  |
| D51 | SA1.13 | Tested software for operational improvements | JIVE | 18 |  |  |
| D71 | SA1.17 | Flexible local GE network | JIVE | 18 |  | 1 |
|  |  | Investigating a 1024M sub-array | JIVE | 20 |  |  |
| D27 | SA1.4 | eMERLIN VSI interfaces design | UniMan | 22 |  | 1 |
| D45 | SA1.9 | Tests using local Jodrell Bank home e-MERLIN telescope | UniMan | 22 |  |  |
| D54 | SA1.15 | VSI Interfaces | JIVE | 23 |  |  |
| D52 | SA1.14 | Test using remote e-MERLIN telescope | UniMan | 24 |  |  |
| D85 | SA1.19 | Multiple e-MERLIN telescope tests | UniMan | 24 |  |  |
| D53 | SA1.16 | VSI support software | JIVE | 26 |  |  |
|  |  | Space craft tracking correlator mode | JIVE | 27 |  |  |
| D12 | SA1.3 | Fast/adaptive scheduling tools | JIVE | 28 |  | 1 |
|  |  | On-the-fly fringe fitting | JIVE | 28 |  |  |
| D84 | SA1.18 | Network monitoring tools | JIVE | 30 |  |  |
|  |  | Real-time download and extraction of station information | JIVE | 30 |  |  |
|  |  | Eighteen months boundary |  |  |  |  |
|  |  | Automated correlator diagnostics | JIVE | 33 |  |  |
|  |  | Removing/adding stations from the correlation process on the fly | JIVE | 34 |  |  |
|  |  | Enhancements & additions to real-time pipeline | JIVE | 36 |  |  |
|  |  | Enhancements & additions to existing monitoring tools | JIVE | 36 |  |  |
| D36 | SA1.7 | Monitored information handling modules | JIVE | 36 |  |  |

The remaining milestones of SA1 have been re-ordered. Note that M23, 24 and 25 (marked in red) were numbered incorrectly in the original contract, and that M19 and M21 were identical. The first three milestones were renumbered, and only M19 has been kept in the following overview.

| M# | AM# | Milestones Description | Lead | Delivery month | Status |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Planned | Actual |  |
| M15 | MSA1.1 | Call for Proposals for e-VLBI service | JIVE | 1 | 1 | 4 |
| M16 | MSA1.2 | Preliminary e-VLBI Service | JIVE | 4 | 4 | 4 |
| M17 | MSA1.3 | Basic data-link technology | JIVE | 6 | 6 | 4 |
| M18 | MSA1.4 | Basic VLBI elements adapted for e-VLBI | JIVE | 6 | 6 | 4 |
| M22 | MSA1.8 | Adaptive network utilization | JIVE | 17 |  |  |
| M20 | MSA1.6 | Enhanced e-VLBI Service | JIVE | 18 |  |  |
| M23 | MSA1.9 | Full bandwidth utilization | JIVE | 26 |  |  |
| M19 | MSA1.5 | Enhanced ToO support | JIVE | 28 |  |  |
| M24 | MSA1.10 | Live e-VLBI system monitoring | JIVE | 30 |  |  |
|  |  | Eighteen months boundary |  |  |  |  |
| M25 | MSA1.11 | Full e-VLBI Service | JIVE | 32 |  |  |

1.3.1.4  SA1: Period 2 Distribution

| P # | Short Name | Period 2 Requested Distribution |
| --- | --- | --- |
| 1 | JIVE | 588,000 € |
| 2 | AARNET | 0 € |
| 3 | DANTE | 0 € |
| 4 | PSNC | 0 € |
| 5 | SURFnet | 0 € |
| 6 | ASTRON | 0 € |
| 7 | CNIG-IGN | 0 € |
| 8 | CSIRO | 0 € |
| 9 | NRF | 0 € |
| 10 | INAF | 0 € |
| 11 | MPG | 0 € |
| 12 | TKK | 0 € |
| 13 | CORNELL | 0 € |
| 14 | UMK | 0 € |
| 15 | OSO | 0 € |
| 16 | SHAO | 0 € |
| 17 | UDEC | 0 € |
| 18 | UNIMAN | 81,375 € |
| 19 | VeA/VIRAC | 0 € |

1.3.1.5  SA1: Gantt Overview

Figure SA1-9: Gantt Overview for Activity SA1

Figure SA1-10: Gantt Overview for Activity SA1, highlighting the next 18 months

1.3.2  SA2: Network Provision for a Global e-VLBI Array

1.3.2.1  SA2: Activity Introduction

As explained in Section A, this specific service activity aims to coordinate the various technical and logistical aspects that are required in order to achieve last-mile connections to the radio telescopes that will form the EXPReS e-VLBI infrastructure. Requesting partial funding from the Commission – in many cases a very small fraction of the total connection cost - it is acting as a significant catalyst, encouraging commercially fair, affordable and competitive quotations, and releasing substantial sources of local and national funding.

During the first year, we have experienced that:

•	SA2 developments are very different for every partner in EXPReS.

•	SA2 expenditures are not flat in time, but uneven and somewhat unpredictable.

•	Most of the expensive infrastructure will be constructed in the second year (March 2007 to February 2008).

•	Some participants have been very successful in obtaining good deals for their high capacity data connections, while others have been able to get the service partially financed by their local government. These activities affect the total cost of their connections, which will generally be lower than expected.

•	The cost associated to SA2 are those of the “last-mile” connections, understanding as such not only the needed equipment and infrastructures from the nearest NREN/GÉANT nodes to the telescopes, but also any other cost related to the transfer of the data to the e-EVN correlator at JIVE.

Special cases are explained below:

a)  JIVE

JIVE is currently connected by SURFnet to GEANT2 at 7 x 1 Gbps, and expects to increase connectivity to 16 x 1 Gbps in the following months. Additionally, a 10 Gbps connection will be made available for testing.  Their connectivity costs, however, will be financed by SURFnet, who should also receive the EC contribution originally assigned to JIVE.

b)  AARNet

Their progress is very much related to participant CSIRO, who could assume the financial commitments, as discussed below. The main contact, George McLaughlin, left in 2006 and a now conversations have resumed with the new CEO, Chris Hancock.

The ATNF/CSIRO telescopes are already linked to AARNet at 1 Gbps, as related in Section A of this report. The international part of the connection, to JIVE, is being investigated. There are two possible scenarios: IP-routing and lightpaths to JIVE.

There are two routed IP paths from ATNF to JIVE. The shortest path has a bottleneck capacity of 155Mbps per connection due to the Perth–Singapore link being four STM-1 undersea circuits. This path uses AARNet3 between Sydney–Perth; AARNet3 between Perth–Singapore; AARNet3 between Singapore–Frankfurt; GÉANT2 from Frankfurt–Amsterdam; and SURFnet between Amsterdam–JIVE. The Perth–Singapore and Singapore–Frankfurt links have been much less reliable than AARNet expected, with several multi-week outages within the last year.

The longer path has a bottleneck link of 1,000Mbps due to gigabit ethernet being used for the AARNet3–CSIRO Sydney customer access link and being used within CSIRO's network. This path uses AARNet3 between Sydney–Seattle; Internet2's Abilene between Seattle–Chicago; GÉANT2 between Chicago–Amsterdam; and SURFnet between Amsterdam–JIVE. This path may alter slightly when Internet2 and NLR merge.

Testing by ATNF to date has mainly used the shorter, bandwidth-constrained path. AARNet has made some router configuration changes to allow different connections between the same machines to be shared across the four STM-1s; previously they would all be placed onto the same STM-1.

ATNF have requested that AARNet route their science traffic via the longer latency-constrained path. This has yet to be done.

Regarding lightpaths to JIVE, AARNet have installed eight gigabit ethernet light paths from its SYD-B point of presence in Rosebery, Sydney to Los Angeles. EXPReS partners on both sides of the connection are currently commissioning and testing these paths. The intent is to use CENIC to transport AARNet's light paths from Los Angeles to Seattle, but CENIC have yet to develop a policy for allocating light paths across their network. There are a number of options for paths from Seattle to JIVE but AARNet has yet to investigate these.

ATNF's equipment generates up to 600Mbps of traffic per telescope. It seems desirable to deliver this to JIVE as three gigabit ethernet circuits, one telescope exclusively using one circuit. A request by one research project for three concurrent trans-Pacific, trans-Atlantic gigabit light paths is unprecedented. How easy or difficult this will be to negotiate with each network operator on the Sydney-JIVE path is unknown yet. As AARNet does not have an automated control plane for light path provisioning, the light paths would be manually established.

c)  SURFnet

SURFnet handles the connectivity of the partners in The Netherlands (JIVE and WSRT/ASTRON). In principle, it had no cost associated (and therefore no EC funding assigned). The connectivity of JIVE is however being provided by SURFnet as well as support for activities such as setup and testing support for lightpaths to our partners.  SURFnet has provided this support since the beginning of the project and we propose to transfer JIVE's SA2 allocation in full to SURFnet.

d)  ASTRON

ASTRON is currently connected directly to JIVE at 1 Gbps via fiber provided by SURFnet. As additional partners come online via lightpaths, ASTRON will consider upgrades to their connection and infrastructure that drives the connection to participate at higher bandwidths. ASTRON is in conversation with SURFnet regarding connectivity.

e)  CNIG-IGN

The construction of the new 40-meter radiotelescope at Yebes is delayed from the original plan. First light is expected in June 2007. The fiber optics connection to GÉANT at 1 Gbps should not be ready before then, as it will be an expensive service payed on a monthly basis. The goal is to build the needed infrastructure in 2007, and start full operations in late 2007 or early 2008, which should continue well after the end of EXPReS. As a consequence of the EXPReS contract, e-VLBI has become a project in the strategic plan of CNIG-IGN, which ensures funding for the next years.

The latest offers from selected communication providers anticipate a cost of service much lower than originally expected, of the order of 50%. Final values will be known at the time of the request for bids call.

f)  CSIRO

The mainland connection was expected to be built before the start of EXPReS, but indeed due to some delays it was finalized within the project. Now all telescopes are connected at 1 Gbps. The problem still to solve, through AARNET, is the international connection and how to deliver the data to JIVE (mentioned above in the AARNet update).  The cost of this participant is much higher than expected, and compensates lower costs for other participants, like INAF, MRO, and/or CNIG-IGN.

g)  HartRAO

The total (shared) international bandwidth for the whole Tertiary Education network (TENET) to which HartRAO attaches is currently 180.5 Mbps, of which some 40 – 75 Mbps is utilized depending on the time of day. The Department of Public Enterprises is to setup a new company, "Infraco", who will open competition for the local connectivity market.

The availability of cables, current or future, into Europe is being investigated.

h)  INAF

INAF operates three radiotelescopes, at Medicina (near Bologna), Noto (Sicily) and Sardinia (under construction). Medicina is already connected, and has participated in successful e-VLBI observations. Their fiber optics connection, expected to be built within EXPReS, was built by the Emiglia-Romana local government after very successful negotiations, which saved the project about 1.4 M€. Now, only relatively small rental costs and equipment is needed to ensure the expected deliverable.

The new Sardinia 64-meter radiotelescope (SRT) is under construction. Its fiber optics connection to Cagliari is now included in the "Sardinia Regional plan for network infrastructure", linked with a PON project (SyberSAR), which is expected to be operational in the summer of 2008. As in the case of Medicina, this comes at no cost for EXPReS therefore saving some 1.3 M€ to the project while ensuring the whole deliverable. There will be costs associated to equipment and the 1 Gbps international lightpath.

i)  MPIfR

The feasibility study is finished and funds are available for the construction of a private fiber optics line from the 100-meter radiotelescope at Effelsberg to Bonn, and then to GÉANT. The expected new date is November 2007 (nine months delay from the original milestone), and will be provided within budget.

j)  MRO

MRO’s 14-m radiotelescope is connected and operating successfully at 10 Gbps.  The total cost estimate for the connection for the committed 5-year fiber lease period rose slightly from the estimated 330ke, to 363ke.  However, CSC/Funet agreed to completely absorb their PoP costs of 230,000 EUR, leaving 133,000 EUR to TKK, of which 89,000 EUR will be accumulated before the end of EXPReS contract.  Additional equipment for 10 Gbps is being purchased which will be used for tests in the EXPReS JRA1 FABRIC.

k)  NAIC

At present, data transfer from the 305-meter Arecibo radiotelescope is possible at 155 Mbps (in practice sometimes only 32 Mbps is reached). Subject to vendor confirmation and availability of funding, the aim is to achieve sustained 1 Gbps rates over 2-3 hours per month. The circuit together with switching equipment will be leased from the telecom provider(s). In early March 2007 a proposal was received from Centennial de Puerto Rico, currently the provider for the Observatory's 155 Mbps ATM-based "last mile" link to the NAP Of The Americas, to upgrade the link to support coordinated burst rates of 512 Mbps using gigabit Ethernet. Recurring costs of this upgrade are substantial and will need to be absorbed into the operating costs of the Observatory and University of Puerto Rico networking partners.  The proposal is under review and a joint decision is expected by mid-April 2007, following which Centennial PR will install the facility.  A further upgrade to 1 Gbps rates is expected to become feasible in May 2007 following Centennial's lighting of a new high-capacity submarine fiber system.

l)  NCU

The 32-meter radiotelescope in Torun is connected and participating in e-VLBI observations since the start of EXPReS. Their main cost is the rental of a 1 Gbps fiber optics line. No changes are expected in their contribution to the project.

m)  ShAO

All four stations (Shanghai, Urumqi, Miyun, Yunnan) have been connect by fiber links from the telescopes to their nearby cities. The cost to EXPReS is the rental of the data transfer service. Discussions with CSTNET are ongoing, to schedule first e-VLBI test observations in 2007, after some delays caused by the breakage of the submarine international fiber optics cable in the December 2006 earthquake, now repaired.

n)  TIGO

The TIGO telescope is connected to University of Concepción at 1 Gbps, and the needed equipment has been purchased. International connection is through REUNA, which increased its backbone from 155 Mbps to 310 Mbps between Concepción and Santiago de Chile, eliminating congestion. Despite its small budget, the participation of TIGO en EXPReS is very important and will provide essential data, as demonstrated by the observations of the SMART-1 satellite crash on the moon. However availability of local resources may limit the amount of observing days offered.

o)  VIRAC

The construction of the last mile dark optical fiber from Irbene to Ventspils International Radioastronomy Center (at a distance of about 30 km) has been completed. The whole EC funding is requested in the first year, and no other commitments are planned in the rest of the project.

1.3.2.2  SA2: Workpackage Summary

| WP# | Description of Workpackage | Lead |
| --- | --- | --- |
| WP1 | Dynamic status report & EXPReS support of the last-mile telescope connections to the nearest (GÉANT) NREN node | SA2 coord. and ALL |
| WP2 | Construction and procurement of equipment for the last-mile infrastructure | All |
| WP3 | Testing of the link and verification of real-time e-VLBI capability | SA2 coord., JIVE and ALL |

1.3.2.3  SA2: Deliverables and Milestones Table

Deliverables for the remainder of the project (months 13-36) are listed below.  Items completed from the first 12 months are not shown.

Five deliverables from the first 12 months are not completed.  These have been identified previously and are the result of external delays.  Additionally, there are modifications to the deliverables table that relate to the slow start for some or our participants.  A delay factor has been added for the following participants:

ShAO  -  3 months

HRAO  -  3 months

NAIC  -  6 months

| D# | AD# | Deliverable Description | Lead | Delivery month | Status |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Planned | Actual |  |
|  | DSA2.06 | Feasibility study of the last-mile connection to the nearest NREN node for participant HRAO | HRAO | 18 |  | ongoing |
|  | DSA2.11 | Equipment of the last-mile infrastructure for participant MRO | MRO | 12 |  | ongoing |
|  | DSA2.12 | Construction and equipment of the last-mile infrastructure for participant CNIG-IGN | CNIG-IGN | 12 |  | ongoing |
|  | DSA2.13 | Construction and equipment of the last-mile infrastructure for participant MPIfR | MPIfR | 12 |  | ongoing |
|  | DSA2.14 | 10 Gbps link upgrade between MERLIN and JIVE | MERLIN JIVE | 18 |  | pendent |
|  | DSA2.15 | e-VLBI test observations, Metsähovi | MRO | 18 | 13 |  |
|  | DSA2.16 | Construction and equipment of the last-mile infrastructure for participant Shanghai | ShAO | 21 |  |  |
|  | DSA2.17 | Construction and equipment of the last-mile infrastructure in AARNET to allow connection of participant CSIRO | AARNET CSIRO | 18 |  |  |
|  | DSA2.18 | Construction and equipment of the last-mile infrastructure for participant Urumqi | ShAO | 21 |  |  |
|  | DSA2.19 | Construction and equipment of the last-mile infrastructure for participant Miyun | ShAO | 21 |  |  |
|  | DSA2.20 | Construction and equipment of the last-mile infrastructure for participant Kunming | ShAO | 21 |  |  |
|  | DSA2.21 | Construction and equipment of the last-mile infrastructure for participant VIRAC | VIRAC | 18 |  |  |
|  | DSA2.22 | Equipment of the last-mile infrastructure for participant NAIC | NAIC | 24 |  |  |
|  | DSA2.23 | Construction and equipment of the last-mile infrastructure for participant TIGO | TIGO | 18 |  |  |
|  | DSA2.24 | AARNET connectivity enhancements | AARNET | 18 |  |  |
|  | DSA2.25 | Feasibility study of the last-mile connection to the nearest GÉANT node for participant INAF (Sardinia) | INAF | 20 |  |  |
|  | DSA2.26 | 10 Gbps link between UniMan and OSO for ultra-VLBI tests | UniMan OSO | 20 |  |  |
|  | DSA2.27 | e-VLBI test observations, Effelsberg | MPIfR | 21 |  |  |
|  | DSA2.28 | e-VLBI test observations, Metsahovi / CSIRO | MRO CSIRO | 22 |  |  |
|  | DSA2.29 | e-VLBI test observations, Yebes | OAN | 22 |  |  |
|  | DSA2.30 | Construction and equipment of the last-mile infrastructure for participant HartRAO | HRAO | 27 |  |  |
|  | DSA2.31 | e-VLBI test observations, Urunqi | ShAO | 33 |  |  |
|  | DSA2.32 | e-VLBI test observations, Mijun | ShAO | 33 |  |  |
|  | DSA2.33 | e-VLBI test observations, Kunming | ShAO | 33 |  |  |
|  | DSA2.34 | e-VLBI test observations, VIRAC | VIRAC | 30 |  |  |

(table continues on next page)

(table continued from previous page)

| D# | AD# | Deliverable Description | Lead | Delivery month | Status |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Planned | Actual |  |
|  | DSA2.35 | e-VLBI test observations, HRAO | HRAO | 33 |  |  |
|  | DSA2.36 | e-VLBI test observations, NAIC, Arecibo | NAIC | 36 |  |  |
|  | DSA2.37 | e-VLBI test observations, TIGO | TIGO | 30 |  |  |
|  | DSA2.38 | Construction and equipment of the last-mile infrastructure for participant INAF (Sardinia) | INAF | 30 |  |  |

A summary of the milestones for the different participants is shown in the next table. MSA2.1 has been accomplished by almost all partners, as explained in Section A of this report. MS2.2 will be met in the second year of the project by several important telescopes (MPIfR and CNIG-IGN). MS2.3 has been accomplished by six telescopes till now, while works for the rest are ongoing.

| M# | AM# | Milestones Description | Lead | Delivery month | Status |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Planned | Actual |  |
| M26 | MSA1.1 | Feasibility study of the last-mile connection to the nearest GÉANT node. | ALL | 6 |  |  |
| M27 | MSA2.2 | Construction and equipment of the last-mile infrastructure. | ALL | 18 |  |  |
| M28 | MSA2.3 | e-VLBI Fringes (Detection). | JIVE and ALL | >10 |  |  |

1.3.2.4  SA2: Period 2 Distribution

| P # | Short Name | Period 2 Requested Distribution |
| --- | --- | --- |
| 1 | JIVE | 0 € |
| 2 | AARNET | 6,000 € |
| 3 | DANTE | 0 € |
| 4 | PSNC | 0 € |
| 5 | SURFnet | 21,000 € |
| 6 | ASTRON | 3,750 € |
| 7 | CNIG-IGN | 50,250 € |
| 8 | CSIRO | 15,000 € |
| 9 | NRF | 4,500 € |
| 10 | INAF | 43,500 € |
| 11 | MPG | 82,500 € |
| 12 | TKK | 6,000 € |
| 13 | CORNELL | 21,000 € |
| 14 | UMK | 15,000 € |
| 15 | OSO | 15,000 € |
| 16 | SHAO | 36,000 € |
| 17 | UDEC | 15,000 € |
| 18 | UNIMAN | 5,250 € |
| 19 | VeA/VIRAC | 22,500 € |

1.3.2.5  SA2: Gantt Overview

Figure SA2-2: SA2 Overview (1 of 2)

Figure SA2-3: SA2 Overview (2 of 2)

1.4  Joint Research Activities

1.4.1  JRA1 - FABRIC

1.4.1.1  JRA1: General Comments

The FABRIC (Future Arrays of Broadband Radio-telescopes on Internet Computing) project researches future technology relevant for the e-VLBI application. It has two major aims, the first being the development of a data-acquisition system that will work with 10 Gbps connectivity, the second to deploy the algorithm of VLBI correlation on Grid computing. After the first year, most of the requirements and design efforts have been completed and work on prototyping is ramping up.

As everywhere, there was some delay finding the right personnel, but the most serious delay originates from making a decision on the technology for the data acquisition development. Boundary conditions are the existing efforts on the PC-EVN system and the so-called Digital Baseband Converters, as well as the requirements from the eMERLIN interface. Finally it was decided to do this project on so called iBOBs (internet Breakout Boards, Univ of Berkeley). The delivery time of these boards and learning to work with this equipment represent delays with respect to the original project plan.

As a result there was also considerable slippage on the overall system analysis document. In October all interfaces had been established at a high level. But the actual document was delayed further as the FABRIC project leader is effectively not available for the project. This document must be delivered in 2007, but in the meantime the necessary interfaces have been agreed and work can progress.

Most of the work-packages can proceed as planned, but where the iBOB systems are required for prototype development, some of the tasks that depend on this are being rescheduled with a new start date.

In the area of the distributed correlator, a large fraction of the work packages were able to start right from the start date of the project. A correlator design document has been drafted but the final version has not been issued. It was decided that the writing of visualization software of the distributed correlator was best postponed until reliable operations were achieved. Moreover, this process can benefit from the effort in SA1.

Strong coordination between WP2.1 and WP2.2 is very important for the success of the distributed correlation effort. A next meeting between JIVE and PSNC staff is planned.  The goal is a more detailed specification of the interfaces between workflow management and the distributed correlator core, including the data flow from the telescope sites.

1.4.1.2  JRA1: Workpackage Summary

WP0 System analysis

Deliver a FABRIC overall design and revised implementation plan (DJ1.5)

WP 1.1.1 Data acquisition architecture

Completed

WP 1.1.2. Data acquisition prototype

Once the prototype iBOB boards with their 10GE interfaces arrive, it is planned to setup a small-scale local testbed with a small COTS 10GE switch, some 10GE-equipped Linux computers, and a set of iBOB FPGA boards, all connected to each other and to the Metsähovi 10GE Internet connection.  We plan to start with establishing the simplest 1/2/4 Gbps UDP-based iBOB FPGA transmitter/receiver firmware first and compare that to the more advanced UDP-Tsunami protocol and determine what is the best implementation tradeoff (e.g. what advanced software features of Tsunami can be reasonably implemented in the FPGA).  The transmitter part will be closely coordinated with Jodrell Bank and Onsala, to ensure that the design is directly applicable to the remote e-MERLIN tests.  The performance levels of 10GE-equipped Linux computers are determined to assess their role and the potential applications for them in the iBOB-10GE data acquisition scheme.

WP 1.1.3. Data acquisition control

This activity can start when the WP 1.1.2 part: "software acquisition/transport” is finished. New manpower will need to be identified for this activity. The work package involves the following components:

•	Identify modules to be added to field system to control new acquisition devices

•	Generate requirements for phase-cal and stats

•	Generate requirements for embedded TSYS calibration

•	Write data acquisition interface document

•	Write and integrate modules for software calibration flow

•	Write and integrate Software performance monitor

•	Test new control modules at telescope

WP 1.2.1. Broadband protocols & multicast

Important work in this area continues as a contributed effort. The work package will be boosted by the transfer of an already identified Research Assistant to this project in July 2007. It will be possible to produce an interim report in month 13, explicitly on the properties of TCP, TCP variants and non TCP protocols. Work on multicasting (strictly multi destination) and on VSI-E tests will be done following the appointment of the protocol person onto FABRIC in July. A final report is expected by the middle of 2008.

WP 1.2.2. Broadband eMERLIN correlator interface

Work in this area is concentrating on the application of iBOB systems, which are becoming available by spring 2007. This effort is closely linked to the engineering the reverse path out of e-MERLIN to e-VLBI in SA1. First fringes are planned with the e-MERLIN correlator for this workpackage in May 2008, but depend critically on the commissioning of that hardware, which is external to EXPReS.

The interface to the e-MERLIN correlator for both SA1 (eMERLIN out) and FABRIC (eMERLIN in) will be implemented using the University of Berkeley's Internet Break Out Boards (iBOB). This card has the functionality required to do both tasks (by changing the FPGA personality).  The boards are expected to be completed in April 2007, with the firmware design expected to be completed by the end of 2007. Tests will take place in 2008 in conjunction with the eMERLIN station boards being produced by NRC Canada. VSI-E will be used for data transport for both input and output. The 4 Gbps iBOB transmitter for Onsala will also be designed, as the eMERLIN out design will be very similar.

Provided the e-MERLIN station boards are delivered on time we hope to make initial fringe tests in May 2008. At the moment the schedule is on track to achieve full operation as on the original plan.

WP 1.2.3. Broadband test

Connectivity at 10 Gbps is expected to be available out of Onsala by October 2007. Onsala is awaiting the delivery of a first iBOB board. This board will be used in conjunction with the Jodrell Bank group in the period before the e-MERLIN correlator is finalized to conduct data transfer tests. These will exercise the data transfer route, test stability of transfer times etc and possibly test different data transfer protocols. Onsala intends to employ someone for 1 man-year funded by EXPReS starting in October 2007 to  conduct these tests,  deal with interfaces to local iBoBs and other local  hardware and coordinate with NRENs the data path issues on the Onsala-Jodrell Bank route.

WP 1.2.4. Public to dedicated network interface

In the coming period the experiment and negotiation activities will be finalized, and the E-LOFAR link to Effelsberg will be ready and tested. Besides the transport of astronomy data, also network based LO signal distribution will be investigated in the upcoming period.

WP 2.1.1. Grid – VLBI collaboration

Completed.

WP 2.1.2. Grid Workflow management

Having the system design completed, work will begin on the implementation of the first prototype version of an e-VLBI system. According to the timeline agreed between JIVE and PSNC, the first prototype will have a somewhat limited functionality, in order to evaluate certain assumptions and proposed solutions. The prototype version will read the data from pre-recorded files, instead of live radio telescopes, creating so called “virtual radio telescopes”. This will be used to test the system feasibility and correlation performance without using valuable radio telescope time. Furthermore, the file servers and computational systems needed to perform a distributed correlation will not be dispersed over the wide-area network, but local PSNC resources will be used instead. This will allow us to complete the required functionality of the workflow management without the need to worry about various networking issues or different hardware/software configurations.

WP 2.1.3 Grid routing

Towards the end of 2007 work will start on deploying the workflow management on truly distributed computing. In this stage, the system will be dispersed among resources provided by the project participants.

WP 2.2.1 Correlator Algorithm design

A first version correlator design document should be finalized in the next few months.  However, we foresee a need to continue updating the document as we learn more from the prototype implementations of the correlator.

WP 2.2.2. Correlator computational core

A large fraction of this work package seems finished, although the results of the software correlator still need to be verified. Additional work has been identified, as software for streaming data into a computational grid will need to be developed at JIVE, and at some point this will need to be deployed at the telescope sites.  This will need to be done towards the end of the next 18 month period.

WP 2.2.3. Scaled up version for clusters

Development of the correlator software itself will be concentrated on scaling things up to compute on cluster computers during the second year (DJ1.21), and computational grids during the first half of the third year (DJ1.28). This entails making the correlator code portable to be deployable at different clusters in an automated sense. Middleware interfaces need to be implemented to allow working with the workflow management. An interesting exercise will be to make load estimates which are an important step in making distributed correlation a truly operational tool.

WP 2.2.5. Interactive visualization

Visualisation software for evaluating the correlator software output will be written when the correlator is able to deliver a complete enough data product.  Critical steps that need to be completed before we can embark on writing that software are:

•	Data emitted by the correlator core (DJ1.13), and

•	Software that automates the generation of correlator delay model.

WP 2.2.6. Output definition

Work has started in this area, transforming the output of the software correlator into the standard product used for data validation of the EVN data processor at JIVE. It is planned that by the middle of 2007 this is sufficiently complete that focus can shift on interactive visualization.

WP 2.2.7. Output merge

By the end of 2008 effort should have started to combine data from multiple compute nodes back into a central data repository. This involves routing the output and sorting the incoming streams into the data archive.

Tests and science demo

First operational use of the software correlator is expected this year when it is to be used to verify interactively station performance connected to standard (disk based) observing sessions.

1.4.1.3  JRA1: Deliverables Table

| D# | AD# | Deliverable Description | Lead | Delivery month | Status |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Planned | Actual |  |
|  | DJ1.3 | Visualization software | JIVE | 21 |  |  |
|  | DJ1.4 | Correlator design specification | JIVE | 13 |  |  |
|  | DJ1.5 | Overall design document | JIVE | 17 |  |  |
| D41 | J1.11 | Protocols performance report | JBO | 13 |  |  |
|  | DJ1.11a | Interim Protocols performance report | JBO | 13 |  |  |
|  | DJ1.11b | Final Protocols performance report | JBO | 28 |  |  |
| D42 | J1.12 | Software correlator core | JIVE | 15 |  |  |
| D43 | J1.13 | Software data product | JIVE | 17 |  |  |
| D66 | J1.14 | Data acquisition interface document | MPI | 22 |  |  |
| D67 | J1.15 | LOFAR station interface report | ASTRON | 21 |  |  |
| D68 | J1.16 | Software for workflow management | PSNC | 18 |  |  |
| D75 | J1.17 | Software for correlation on cluster | JIVE | 23 |  |  |
| D76 | J1.18 | Data acquisition test report | MPI | 26 |  |  |
| D77 | J1.19 | Data acquisition prototype at telescope | MRO/OSO | 26 |  |  |
| D78 | J1.20 | Overall broadband demonstration | OSO | 33 |  |  |
| D79 | J1.21 | Software cluster correlation | JIVE | 23 |  |  |
| D80 | J1.22 | First fringes software correlator | JIVE | 23 |  |  |
| D87 | J1.23 | Software to collect distributed output | JIVE | 30 |  |  |
| D92 | J1.24 | Software to create data product from distributed correlation | JIVE | 31 |  |  |
| D93 | J1.25 | Software routing | PSNC | 29 |  |  |
| D105 | J1.26 | eMERLIN interface available | JBO | 30 |  |  |
| D106 | J1.27 | Fringes with new routing | JIVE | 31 |  |  |
| D108 | J1.28 | Software distributed correlation | JIVE | 33 |  |  |
| D109 | J1.29 | First fringes Grid correlator | JIVE | 34 |  |  |
| D110 | J1.30 | First fringes on FABRIC | JIVE | 35 |  |  |
| D118 | J1.31 | Final report | JIVE | 36 |  |  |

1.4.1.4  JRA1: Period 2 Distribution

| P # | Short Name | Period 2 Requested Distribution |
| --- | --- | --- |
| 1 | JIVE | 243,000 € |
| 2 | AARNET | 0 € |
| 3 | DANTE | 0 € |
| 4 | PSNC | 81,000 € |
| 5 | SURFnet | 0 € |
| 6 | ASTRON | 20,250 € |
| 7 | CNIG-IGN | 0 € |
| 8 | CSIRO | 0 € |
| 9 | NRF | 0 € |
| 10 | INAF | 0 € |
| 11 | MPG | 59,250 € |
| 12 | TKK | 96,000 € |
| 13 | CORNELL | 0 € |
| 14 | UMK | 0 € |
| 15 | OSO | 51,750 € |
| 16 | SHAO | 0 € |
| 17 | UDEC | 0 € |
| 18 | UNIMAN | 96,000 € |
| 19 | VeA/VIRAC | 0 € |

1.4.1.5  JRA1: Gantt Overview

Figure JRA1-9: Gantt Overview for Activity FABRIC WP1.

Figure JRA1-10: Gantt Overview for Activity FABRIC WP2.

2.  Appendices to Technical Annex 1

2.1  Appendix:  Addendum to the Consortium Agreement

EXPReS partners have individually signed the addendum to the Consortium Agreement.  Below, the core text of the document is provided and the first example of the signatory page.  The remaining 18 pages of mostly empty documents have been omitted.  The full, signed agreement is archived at the project office.

2.2  Appendix:  M.I.T. Contract

# MASSACHUSETTS INSTITUTE OF TECHNOLOGY

# OFFICE OF SPONSORED PROGRAMS

AGREEMENT (the “Agreement”) between the Massachusetts Institute of Technology, hereinafter referred to as  “M.I.T.,” and Joint Institute for VLBI in Europe, represented  by (insert here), hereinafter referred to as the “Sponsor.”

# This Agreement is entered into as of January 1, 2007 the “Effective Date.”

WHEREAS, the effort contemplated by this Agreement is of mutual interest and benefit to M.I.T., the VLBI Community,  and to the Sponsor, and will further the instructional and research objectives of M.I.T. in a manner consistent with its status as a non-profit, tax-exempt, educational  institution,

NOW, THEREFORE, the parties hereto agree as follows:

1.  	STATEMENT OF WORK. M.I.T. agrees to use all reasonable efforts to perform the project as set forth in Exhibit A for the “Support and Development of Mark 5 VLBI Data Systems for e-VLBI Applications”. M.I.T. shall provide Sponsor with any knowledge, insights and know-how which has been acquired in performance of the project and M.I.T. will, in an appropriate manner, continuously inform Sponsor of the results of the research work.

After the completion of the research work, M.I.T. will submit a final written report to Sponsor. Sponsor is entitled to use the contents of the final report for its non-commercial research purposes. M.I.T. will endeavour to prepare and deliver the final report in a timely manner.

2.  	PRINCIPAL INVESTIGATOR.  The project will be supervised by Dr. Alan Whitney, Haystack Observatory, the “Principal Investigator.”  If, for any reason, he is unable to continue to serve as Principal Investigator, and a successor acceptable to both M.I.T. and the Sponsor is not available, this Agreement shall be terminated as provided in Article 6.

3.  	PERIOD OF PERFORMANCE.  The project shall be conducted during the period January 1, 2007 (the “Starting Date”) through September 30, 2007  (the “Completion Date”). The Completion Date will be subject to extension only by mutual written agreement of the parties.

4.  	REIMBURSEMENT OF COSTS.  In consideration of the foregoing, the Sponsor will reimburse M.I.T. for all direct and F&A (Facilities & Administrative, or indirect) costs incurred in the performance of the project, which shall not exceed the total estimated project cost of $66,200 without written authorization from the Sponsor.

5.  	PAYMENT.  Payments shall be made to M.I.T. by the Sponsor as follows:

90 %  in advance

10 % upon delivery of final report

in U.S. dollars, net of taxes or impost of any kind. A final financial accounting of all

costs incurred and all funds received by M.I.T. hereunder together with a check

for the amount of the unexpended balance, if any shall be submitted to the Sponsor

within ninety days following the Completion Date.

MASSACHUSETTS INSTITUTE 			SPONSOR

# OF TECHNOLOGY

Laureen Augustine

Senior Contract Administrator

E19-750, OSP

Massachusetts Institute of Technology

77 Massachusetts Ave.

Cambridge,  MA  02139  USA

laureena@mit.edu

Phone: (617) 253-3922

FAX  : (617) 253-4734

6.  	TERMINATION.  Performance under this Agreement may be terminated by the Sponsor upon sixty (60) days’ prior written notice.  Performance may be terminated by M.I.T. (1) if the Sponsor fails to make payment to M.I.T. in accordance with the payment schedule stated in Article 5 above and does not remedy the non-payment within thirty (30) days’ written notice from M.I.T. or (2) if circumstances beyond M.I.T.’s reasonable control preclude continuation of the Research. Upon termination by either party, M.I.T. will be reimbursed as specified in Article 4 for all costs and non-cancelable commitments incurred in the performance of the Research up to and including the effective date of termination, such reimbursement not to exceed the total estimated project cost specified in Article 4.

7.    PUBLICATIONS.  M.I.T. will be free to publish the results of the Research after providing the Sponsor with a thirty (30) day period in which to review each publication to identify patentable subject matter and to identify any inadvertent disclosure of the Sponsor's proprietary information. If necessary to permit the preparation and filing of U.S. patent applications, the Principal Investigator may agree to an additional review period not to exceed sixty (60) days. Any further extension will require subsequent agreement between the Sponsor and M.I.T.

8.	INTELLECTUAL PROPERTY.

- Title to any invention conceived or first reduced to practice in the performance of the project shall remain with M.I.T., which shall have the sole right to determine the disposition of any inventions or other rights resulting therefrom, including the right to determine whether or not a patent application shall be filed.  M.I.T., however, shall notify the Sponsor of its determination, and if a patent applicatin is filed on such invention, M.I.T. shall grant to the Sponsor a non-exclusive, non-commercial, non-transferable, royalty-free license to use such invention for internal research purposes only.

- Title to and the right to determine the disposition of any copyrights or copyrightable material first produced or composed in the performance of this effort shall remain with M.I.T.  M.I.T. shall grant to the Sponsor an irrevocable, royalty-free, non-transferable, non-exclusive right and license to use, reproduce, make derivative works, display, distribute, and perform all such copyrightable materials other than computer software and its documentation and/or informational databases.  M.I.T. shall grant to the Sponsor an irrevocable, royalty-free, non-transferable, non-exclusive right and license to use, reproduce, make derivative works, display, and perform computer software and its documentation, and/or databases specified to be developed and delivered under the Statement of Work for Sponsor's internal (non-commercial)  research purposes.

C. 	TITLE TO JOINT INVENTIONS.  Inventions made jointly by employees and/or students of M.I.T. and employees of the Sponsor in the performance of the Research, or inventions made solely by employees of the Sponsor with use of M.I.T. facilities (“Joint Inventions”) shall be jointly owned by the parties. The Sponsor shall be notified of any Joint Invention promptly after an invention disclosure is received by the M.I.T. Technology Licensing Office. Within ninty (90) days of M.I.T.’s written notification to the Sponsor of a Joint Invention disclosure, upon the Sponsor’s written request to the M.I.T. Technology Licensing Office and M.I.T.’s approval thereof, the Sponsor shall have the first right to file patent applications on Joint Inventions in the names of both parties.  All expenses incurred in obtaining and maintaining any patent on such invention shall be equally shared except that if one party declines to share in such expenses, the other party may take over the prosecution and maintenance thereof, at its own expense, provided that title to the patent remains in the names of both parties.

9.	REPRESENTATIONS AND WARRANTIES.  M.I.T. MAKES NO REPRESENTATIONS OR WARRANTIES OF ANY KIND, EXPRESS OR IMPLIED, CONCERNING THE RESEARCH OR ANY INTELLECTUAL PROPERTY RIGHTS,  INCLUDING, WITHOUT LIMITATION, WARRANTIES OF MERCHANTABILITY, FITNESS FOR A PARTICULAR PURPOSE, NONINFRINGEMENT, VALIDITY OF ANY INTELLECTUAL PROPERTY RIGHTS OR CLAIMS, WHETHER ISSUED OR PENDING, AND THE ABSENCE OF LATENT OR OTHER DEFECTS, WHETHER OR NOT DISCOVERABLE.  Specifically, and not to limit the foregoing, M.I.T. makes no warranty or representation (i) regarding the validity or scope of the Research or any intellectual property rights optioned or granted hereunder and (ii) that the exploitation of the Research or any intellectual property rights will not infringe any patents or other intellectual property rights of M.I.T. or of a third party.

IN NO EVENT SHALL M.I.T., ITS TRUSTEES, DIRECTORS, OFFICERS, EMPLOYEES, STUDENTS AND AFFILIATES, BE LIABLE FOR INCIDENTAL OR CONSEQUENTIAL DAMAGES OF ANY KIND, INCLUDING ECONOMIC DAMAGES OR INJURY TO PERSONS OR PROPERTY AND LOST PROFITS, REGARDLESS OF WHETHER M.I.T. SHALL BE ADVISED, SHALL HAVE OTHER REASON TO KNOW OR IN FACT SHALL KNOW OF THE POSSIBILITY OF THE FOREGOING.  THIS  ARTICLE 11 SHALL SURVIVE THE EXPIRATION OR ANY EARLIER TERMINATION OF THIS AGREEMENT.

Each party hereto agrees to be responsible for its own negligent acts and omissions to the full extent required by law.

10.	USE OF NAMES.  Neither party will use the name of the other in any advertising or other form of publicity without the written permission of the other.  As an example for M.I.T., the Sponsor shall not use the name of “Massachusetts Institute of Technology,” “Lincoln Laboratory,” Haystack Observatory or any variation, adaptation or abbreviation thereof, or that of any of its trustees, officers, faculty, students, employees or agents or any trademark owned by M.I.T.  For M.I.T., the Director of the M.I.T. News Office has authority to grant to the Sponsor any approved use of the M.I.T. name.

11.	ASSIGNMENT.  This Agreement shall be binding upon and inure to the benefit of the parties hereto and the successors to substantially the entire business and assets of the respective parties hereto.  This Agreement shall not be assignable by either party without the prior written consent of the other party; any attempted assignment is void.

- GOVERNING LAW.  The validity and interpretation of this Agreement and the legal relationship of the parties to it shall be governed by the laws of the Commonwealth of Massachusetts and the applicable U.S. Federal law.

13.  GOVERNING LANGUAGE.  In the event that a translation of this Agreement is prepared and signed by the parties for the convenience of the Contractor, this English language version shall be the official version and shall govern if there is a conflict between the two.

14.	FORCE MAJEURE.  Neither party shall be responsible to the other for failure to perform any of the obligations imposed by this Agreement, provided such failure shall be occasioned by fire, flood, explosion, lightning, windstorm, earthquake, subsidence of soil, failure or destruction, in whole or in part, of machinery or equipment or failure of supply of materials, discontinuity in the supply of power, governmental interference, civil commotion, riot, war, strikes, labor disturbance, transportation difficulties, labor shortage or any cause beyond its reasonable control.

15.	EXPORT CONTROLS.  It is understood that M.I.T. is subject to United States laws and regulations controlling the export of technical data, computer software, laboratory prototypes and other commodities, and that its obligations hereunder are contingent on compliance with applicable U.S. export laws and regulations (including the Arms Export Control Act, as amended, and the Export Administration Act of 1979).  The transfer of certain technical data and commodities may require a license from the cognizant agency of the United States Government and/or written assurances by the Sponsor that the Sponsor will not re-export data or commodities to certain foreign countries without prior approval of the cognizant government agency.  While M.I.T. agrees to cooperate in securing any license which the cognizant agency deems necessary in connection with this Agreement, M.I.T. cannot guarantee that such licenses will be granted.

16.	ENTIRE AGREEMENT.  Unless otherwise specified, this Agreement and its Attachments embody the entire understanding between M.I.T. and the Sponsor for the project, and any prior or contemporaneous representations, either oral or written, are hereby superseded.  No amendments or changes to this Agreement, including without limitation, changes in the statement of work, total estimated cost, and period of performance, shall be effective unless made in writing and signed by authorized representatives of the parties.

MASSACHUSETTS INSTITUTE 			SPONSOR

# OF TECHNOLOGY

By  		Stephen J. McAlarney				By

Title 	Associate Director			 	Title

Date 							Date

2.4  Appendix: Form C's

The following pages contain scans from each partners' Form C

JIVE

AARNET

DANTE

PSNC

SURFnet

ASTRON

CNIG-IGN

CSIRO

HARTRAO

INAF

MPIfR

MRO

NAIC

NCU

OSO

ShAO

TIGO

UniMan

VIRAC

2.5  Appendix: Audit Certificates

The following pages contain the Audit Certificates for the following partners:

JIVE

PSNC

CSIRO

INAF

MPIfR

MRO

OSO

ShAO

TIGO

UniMan

VIRAC